PROTOFIRE

Project Governance & Security Policy Framework

CL-PHASE-001

Audit-Ready Phase Checklists — All 12 Phases

Track A (Internal Delivery)  |  Track B (Client Co-Delivery)

| Document ID | CL-PHASE-001 |
| --- | --- |
| Version | 1.0 |
| Status | Draft — Pending Approval |
| Date | March 2026 |
| Owner | CISO |
| Approver | Node Owner + Director of Engineering |
| Classification | Confidential — Internal |
| Source Framework | GRC-PF-001 v1.0 |
| Phases Covered | 1–12 (Assessment through New Deployments) |
| Track Coverage | Track A & Track B throughout |
| Audit Standard | ISO/IEC 27001:2022 Cl.9 · SOC 2 |
| Step Fields | 18 fields per step (complete audit trail) |
| Total Steps | 42 checklist steps across 12 phases |

CONFIDENTIAL — INTERNAL USE AND APPROVED AUDITORS ONLY

# Phase 1: Assessment

| PRE-SALES | Track A + Track B — same process; Track B adds client-facing risk communication in step AM-003 |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 1 |
| --- | --- |
| Phase Name | Assessment |
| Phase Objective | Determine whether the engagement is commercially viable, structurally manageable, and security-sound before any commercial commitment is made. Assign a Composite Risk Score (C/B/P model). Identify Hard Stop conditions. Do NOT treat this as a security assessment in isolation — assess structural manageability, irreversibility, custody risk, and economic attack surface simultaneously. |
| Entry Criteria | Potential client or internal project opportunity has been identified Account Manager has initial project description or brief No commercial commitment has been made (no SOW, MSA, or LOI signed) |
| Exit Criteria | C/B/P Composite Risk Score calculated and documented Risk tier (T1–T4) assigned All 7 Hard Stop conditions checked; no open HS conditions, or HS conditions documented with escalation plan Protocol class identified Jurisdiction cleared (not OFAC-listed) Go / No-Go decision recorded with sign-off |
| Key Phase Risks | C3 — OFAC/sanctioned jurisdiction not identified early (HS-01 trigger) P3 — TVL > USD 1M without audit budget identified → HS-03 pre-trigger REPUT-01 — Brand association risk (high-risk protocol design) ECON-01 — Economic attack surface present but not flagged B3 — No contractual protections visible in initial brief |
| Key Control Objectives | C/B/P risk scoring methodology applied uniformly and completely OFAC/FATF jurisdiction check mandatory before any scoring Hard Stop conditions evaluated per HS-01 through HS-07 checklist Risk tier assigned before Gate G1-A sign-off Composite Score recalculated if any material change occurs post-Assessment |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — same process; Track B adds client-facing risk communication in step AM-003 |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-1-Assessment/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-01/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P1-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx Example: ACME-BRIDGE-P1-AM-001-v1.0-20260310-APPROVED.docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | 5 years from engagement close (Gate decisions); 7 years if contract is subsequently signed |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| AM | Account Manager | R | Leads assessment; completes C/B/P scoring; runs OFAC check; records Go/No-Go decision | Approves Gate G1-A outcome within mandate; escalates T3/T4 to Node Owner |
| NO | Node Owner | A | Accountable for Go/No-Go decision; reviews scoring; approves hard-stop escalation plans | Final approver for Gate G1-A; signs assessment record for T2+ engagements |
| CISO | vCISO | C | Consulted on protocol class, irreversibility, custody ambiguity, economic risk; reviews for T3/T4 | Must co-approve any engagement with Score ≥ 3.0 (T3/T4) |
| TL | Technical Lead | C | Provides input on technical complexity (P1); protocol class; upgrade/pause feasibility | N/A at this phase; advisory only |
| PM | Project Manager | C | Provides input on team capability (P2) and delivery timeline feasibility | N/A |
| fCTO | Field CTO | C | Required for novel protocol or cross-chain architecture assessment (T3/T4 only) | Co-sign for T3/T4 technical assessment |
| SE | Sales Engineer | C | Supports technical brief clarification; initial scoping of complexity | N/A |

## 3. Role-Based Checklist

| P1-AM-001 Collect and document project brief [TRACK A + B] |  |
| --- | --- |
| Step ID | P1-AM-001 |
| Phase | Phase 1 — Assessment |
| Role | Account Manager (AM) |
| Control Objective | Ensure complete information is collected before risk scoring begins, preventing material misclassification of engagement risk. |
| Action | Collect and document project brief |
| Detailed Instruction | Obtain the initial project brief from the client or internal source. Collect: (1) Proposed protocol type (DeFi / bridge / wallet / dApp / Web3 standard / non-Web3); (2) Estimated TVL or value-at-risk; (3) Target chain(s) and jurisdiction of client entity; (4) Proposed timeline; (5) Any existing audit requirements stated by client; (6) Public attribution requirements (will client name Protofire publicly?); (7) Any known technical constraints. Record all answers in the Assessment Brief template. If the client cannot answer TVL or chain at this stage, record "Unknown" and treat as worst-case in scoring (see P1-AM-002). |
| Required Input | Client briefing document, email thread, or intake call notes. Assessment Brief template (template ref: CL-401). |
| Method / Calculation / Assessment | Structured intake using Assessment Brief template. Each item scored as Known / Unknown / Refused. Unknown TVL defaults to "assume >$1M" for P3 sub-scoring. Unknown jurisdiction defaults to "Non-FATF" for C3. |
| Expected Output | Completed Assessment Brief with all 7 information items recorded. Status for each: Known / Unknown (with default applied). |
| Evidence Required | Assessment Brief document (completed and dated). Email or meeting notes confirming source of information. Version-controlled in GW project folder. |
| Approval Required | Node Owner — review and acknowledgement before scoring commences for any engagement where Deal Size > $200K or protocol is DeFi/Bridge. |
| Acceptance Criteria | All 7 information items have a recorded status. No item is blank. Default values applied and documented for all "Unknown" items. Assessment Brief is version-controlled. |
| Related Risk | REPUT-01 (brand association if client type is misclassified); C4 (client type scoring depends on information quality) |
| Related Control | Information completeness check — prevents mispriced risk from incomplete data |
| Related Policy / Standard Clause | POL-003 §2 (C/B/P Risk Scoring Framework); STD-101 Step 1 Preventive Controls |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-1-Assessment/P1-AM-001-Assessment-Brief-v1.0-[DATE].docx Repository: /docs/governance/phase-01/assessment-brief.md |
| Audit Relevance | Auditors verify that risk scoring was based on documented facts, not verbal recollection. Assessment Brief is the primary source document for the C/B/P scoring worksheet. |
| Notes / Exceptions | If client refuses to provide TVL or jurisdiction, escalate to Node Owner before proceeding. A refusal is itself a C4 indicator (Anonymous = Score 4). Track B: Brief should be prepared jointly with client contact where possible to improve data quality. |

| P1-AM-002 Complete C/B/P Composite Risk Scoring Worksheet [TRACK A + B] |  |
| --- | --- |
| Step ID | P1-AM-002 |
| Phase | Phase 1 — Assessment |
| Role | Account Manager (AM) |
| Control Objective | Quantify the composite risk of the engagement objectively using the standardized three-pillar scoring model before any commercial commitment. |
| Action | Complete C/B/P Composite Risk Scoring Worksheet |
| Detailed Instruction | Using the Assessment Brief from P1-AM-001, complete the C/B/P scoring worksheet: PILLAR C (Client Risk, 30% weight): Score each sub-factor 1–4: C1 Deal Size: <$50K=1 ¦ $50K–$200K=2 ¦ $200K–$1M=3 ¦ >$1M=4 C2 Portfolio Concentration: <20% Node revenue=1 ¦ 20–40%=2 ¦ 40–60%=3 ¦ >60%=4 (→ HS-04 if 4) C3 Jurisdiction: FATF low-risk=1 ¦ FATF medium=2 ¦ Non-FATF=3 ¦ OFAC=4 (→ HS-01 IMMEDIATE STOP) C4 Client Type: Established DAO/corp=1 ¦ Funded start-up=2 ¦ Unaudited project=3 ¦ Anonymous=4 PILLAR B (Business Risk, 35% weight): B1 Payment Terms: Full upfront=1 ¦ Milestone=2 ¦ Monthly=3 ¦ Deferred=4 B2 Payment History: Excellent=1 ¦ Good=2 ¦ Delayed=3 ¦ Arrears>60d=4 (→ HS-05) B3 Contractual Protections: MSA+IP+LoL=1 ¦ MSA only=2 ¦ LOI=3 ¦ None=4 (→ HS-02 if no MSA proceeds to Phase 4) B4 Revenue Diversification: Client share <20%=1 ¦ 20–40%=2 ¦ 40–60%=3 ¦ >60%=4 PILLAR P (Project Risk, 35% weight): P1 Technical Complexity: Standard Web2=1 ¦ Web3 dApp=2 ¦ DeFi/Bridge=3 ¦ Novel chain=4 P2 Team Capability: Domain experts available=1 ¦ Experienced=2 ¦ Learning curve=3 ¦ Unproven=4 P3 TVL / Value at Risk: <$100K=1 ¦ $100K–$1M=2 ¦ $1M–$10M=3 ¦ >$10M=4 (→ HS-03 pre-trigger if 3 or 4 without audit budget) P4 Liability Exposure: Capped LoL clause=1 ¦ Partial cap=2 ¦ Soft cap=3 ¦ No cap=4 P5 Audit Requirement: Not required=1 ¦ External planned=2 ¦ Required but unpaid=3 ¦ Client refuses=4 Calculate: C_score = (C1+C2+C3+C4) / 4 B_score = (B1+B2+B3+B4) / 4 P_score = (P1+P2+P3+P4+P5) / 5 Composite = (C_score × 0.30) + (B_score × 0.35) + (P_score × 0.35) Assign Tier: 1.0–1.9=T1 (Low) ¦ 2.0–2.9=T2 (Medium) ¦ 3.0–3.5=T3 (High) ¦ 3.6–4.0=T4 (Critical) |
| Required Input | Assessment Brief (P1-AM-001 output). Prior payment history from Finance/Billing for existing clients (request via FIN if applicable). Node revenue figures for C2/B4 from Resource Manager. |
| Method / Calculation / Assessment | Formula: Composite = (C×0.30) + (B×0.35) + (P×0.35). All sub-factors scored 1–4. Weighted average produces Composite 1.0–4.0. Must be performed in the Excel scoring template or equivalent; manual calculation is insufficient without a calculation record. |
| Expected Output | Completed C/B/P scoring worksheet with all 13 sub-factors scored, pillar scores calculated, composite score, and risk tier assigned. Worksheet dated and signed by AM. |
| Evidence Required | Completed scoring worksheet (Excel or equivalent) saved to GW project folder, version-controlled. Node Owner sign-off cell completed for T2+ engagements. |
| Approval Required | Node Owner must review and countersign for T2 (Score ≥ 2.0). Node Owner + vCISO must review for T3/T4 (Score ≥ 3.0). |
| Acceptance Criteria | All 13 sub-factors have a score (1–4). Formula is verified (pillar scores sum correctly to composite). Risk tier is assigned. If any sub-factor scores 4 (maximum), Hard Stop implications are documented. Sign-off completed at appropriate authority level. |
| Related Risk | All C/B/P risks — this step quantifies them all |
| Related Control | Risk scoring standardization — prevents subjective risk assessment |
| Related Policy / Standard Clause | POL-003 §2 (C/B/P Risk Scoring Framework, full scoring table); STD-101 Step 1 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-1-Assessment/P1-AM-002-CBP-Scoring-v1.0-[DATE].xlsx Repository: not required (contains commercial-sensitive data) |
| Audit Relevance | This is the primary quantitative risk evidence for the engagement. Auditors will verify (a) all sub-factors are scored, (b) calculation is correct, (c) approval authority is commensurate with risk tier, (d) no sub-factor with Hard Stop implications was overlooked. |
| Notes / Exceptions | If Composite changes materially (>0.5 points) at any subsequent phase, the worksheet must be updated and re-signed. Track B: Score C2 (concentration) based on Node-level revenue, not project-level. |

| P1-AM-003 Verify all 7 Hard Stop conditions [TRACK A + B] |  |
| --- | --- |
| Step ID | P1-AM-003 |
| Phase | Phase 1 — Assessment |
| Role | Account Manager (AM) |
| Control Objective | Identify all Hard Stop conditions before any commercial commitment, preventing Protofire from entering engagements that are structurally prohibited. |
| Action | Verify all 7 Hard Stop conditions |
| Detailed Instruction | Check each Hard Stop condition against the Assessment Brief and scoring worksheet: HS-01 OFAC Jurisdiction: Confirm C3 ≠ 4. If C3=4 (OFAC-listed), STOP IMMEDIATELY. No further action. Notify Node Owner and vCISO within 1 hour. Do not communicate further with potential client pending legal review. HS-02 No MSA: Confirm that the engagement will not proceed to Phase 4 (Kickoff) without a signed MSA. At Phase 1, this is a forward planning check — document that MSA will be required. HS-03 TVL without audit: If P3 ≥ 3 (TVL > $1M), confirm that external audit budget is either included in the scope or explicitly acknowledged by client. If client refuses audit for TVL > $1M, score P5=4 and document the pre-trigger. HS-04 Concentration: If C2=4 (>60% Node revenue), document and flag for GRC review before proceeding to Proposal. HS-05 Payment Arrears: If B2=4 (existing client with arrears >60 days), escalate to Finance and Node Owner before proceeding. HS-06 Irreversibility Gate: At Phase 1, document whether the protocol involves irreversible on-chain operations. This is a forward planning check only. HS-07 Custody Ambiguity: At Phase 1, document key ownership intent. If ambiguous, flag as a risk — resolution is required before Phase 9. |
| Required Input | C/B/P scoring worksheet (P1-AM-002). Assessment Brief. Finance report on payment history (B2) for existing clients. |
| Method / Calculation / Assessment | Checklist verification against each HS-01 through HS-07. Binary outcome per condition: CLEAR / TRIGGERED. If TRIGGERED: document the condition, the action required, and who was notified. |
| Expected Output | Hard Stop verification record with status for each of the 7 conditions. Any TRIGGERED condition must have an escalation record. |
| Evidence Required | Hard Stop Verification Checklist (signed by AM, countersigned by NO for any TRIGGERED condition). Escalation email or Slack message with timestamp for any TRIGGERED condition. |
| Approval Required | Node Owner must sign Hard Stop Verification Record for all T2+ engagements. vCISO must co-sign for any HS-03 or HS-04 condition identified. |
| Acceptance Criteria | All 7 conditions evaluated. Each condition shows status CLEAR or TRIGGERED. No TRIGGERED condition is unaddressed. For any TRIGGERED HS-01 condition, engagement is immediately suspended. |
| Related Risk | HS-01 (OFAC); HS-02 (no MSA); HS-03 (TVL/no audit); HS-04 (concentration); HS-05 (arrears); HS-06 (irreversibility); HS-07 (custody) |
| Related Control | Hard Stop mandatory check — prevents engagement with structurally prohibited conditions |
| Related Policy / Standard Clause | POL-001 §5.3 (Hard Stop Conditions HS-01 through HS-07); STD-101 Step 1 Hard Stop column |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-1-Assessment/P1-AM-003-HardStop-Check-v1.0-[DATE].docx |
| Audit Relevance | Auditors treat any undocumented Hard Stop check as a control failure regardless of outcome. The record must show the check was performed before commercial terms were discussed, not after. |
| Notes / Exceptions | HS-01 is non-waivable under any circumstances (POL-009 §3). Track B: for client-co-delivery, the client representative must also be informed of any HS-04 condition affecting their engagement. |

| P1-NO-001 Gate G1-A: Review scoring, assign risk tier, record Go / No-Go decision [TRACK A + B] |  |
| --- | --- |
| Step ID | P1-NO-001 |
| Phase | Phase 1 — Assessment |
| Role | Node Owner (NO) |
| Control Objective | Confirm Gate G1-A is cleared with documented accountability and that the risk tier assignment drives appropriate governance intensity going forward. |
| Action | Gate G1-A: Review scoring, assign risk tier, record Go / No-Go decision |
| Detailed Instruction | Review the completed C/B/P scoring worksheet (P1-AM-002) and Hard Stop Verification Checklist (P1-AM-003). Verify: 1. All 13 sub-factors are scored and calculations are correct (manually verify the formula if in doubt). 2. All 7 Hard Stop conditions are evaluated and no open TRIGGERED condition exists without an escalation plan. 3. The protocol class has been identified and any irreversibility risk is noted. 4. The risk tier is appropriate given the scores. If Risk Tier is T1 or T2: Node Owner alone makes the Gate G1-A Go/No-Go decision. If Risk Tier is T3 or T4: Node Owner must obtain vCISO advisory opinion before signing Gate G1-A. Document vCISO input (email or meeting note) in the gate record. Record the decision: Go (proceed to Phase 2) / No-Go (engagement declined — document reason) / Go-with-Conditions (proceed to Phase 2 with specific remediations required, documented in gate record, and a follow-up check at Phase 3 gate). For Go-with-Conditions: define the condition, the responsible person, and the deadline for resolution. The condition must be resolved and recorded before Phase 3 (MSA) gate. |
| Required Input | C/B/P Scoring Worksheet (P1-AM-002); Hard Stop Verification Checklist (P1-AM-003); Assessment Brief (P1-AM-001). |
| Method / Calculation / Assessment | Review and sign-off of submitted documents. If Node Owner identifies any calculation error, scoring error, or missed Hard Stop: return to AM for correction before signing. |
| Expected Output | Gate G1-A Decision Record: dated, signed by Node Owner (and vCISO for T3/T4), with decision (Go / No-Go / Go-with-Conditions) and rationale. |
| Evidence Required | Gate G1-A Decision Record (signed). Email or Slack confirmation from vCISO (for T3/T4). Any Go-with-Conditions remediation plan attached. |
| Approval Required | Node Owner (T1/T2). Node Owner + vCISO (T3/T4). |
| Acceptance Criteria | Gate record is dated, signed, and specifies Go / No-Go / Go-with-Conditions. For T3/T4, vCISO input is documented. No Go-with-Conditions proceeds without a documented remediation plan with deadline. |
| Related Risk | ALL Phase 1 risks — this gate locks the risk assessment and authorizes commercial progression |
| Related Control | Gate G1-A control — mandatory sequential progression check per STD-101 |
| Related Policy / Standard Clause | POL-001 §5.2 (Gate Criteria); STD-101 Step 1 Gate column; POL-003 §2 (risk tier acceptance table) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-1-Assessment/P1-NO-001-Gate-G1A-Decision-v1.0-[DATE].docx |
| Audit Relevance | Gate records are primary audit evidence for sequential lifecycle compliance. An auditor will verify that Phase 2 was not started before this gate was signed. Timestamp on gate record must precede any Phase 2 activity timestamps. |
| Notes / Exceptions | If the Gate G1-A is returned for correction (e.g., calculation error found), the corrected worksheet must be versioned (v1.1, v1.2) and the gate record must reference the corrected version. |

| P1-vCISO-001 Conduct risk advisory review for T3/T4 engagements (Score ≥ 3.0) [TRACK A + B] |  |
| --- | --- |
| Step ID | P1-vCISO-001 |
| Phase | Phase 1 — Assessment |
| Role | vCISO |
| Control Objective | Ensure that any T3/T4 engagement has had independent security and risk review before commercial commitment. |
| Action | Conduct risk advisory review for T3/T4 engagements (Score ≥ 3.0) |
| Detailed Instruction | Triggered only when Composite Score ≥ 3.0. Review the C/B/P worksheet and assessment brief. Focus on: 1. Protocol class risk — is the stated complexity consistent with the brief? 2. TVL / custody risk — is HS-03 / HS-07 properly flagged? 3. Economic attack surface — for DeFi/bridge, are ECON-01 and BRIDGE-01 risks acknowledged? 4. Irreversibility — is CHAIN-FATAL-01 flagged if on-chain protocol is involved? 5. Any OFAC / legal jurisdiction concern not adequately addressed. Provide written advisory opinion (email is acceptable) to Node Owner stating: (a) specific concerns identified; (b) whether scoring appears accurate; (c) any mandatory conditions to attach to Gate G1-A Go-with-Conditions outcome. For Score ≥ 3.5 (T4): attend Node Owner Gate G1-A review meeting and co-sign gate record. |
| Required Input | C/B/P Scoring Worksheet; Hard Stop Verification Checklist; Assessment Brief. |
| Method / Calculation / Assessment | Expert review against STD-101 Phase 1 risk categories and POL-003 phase-specific risk register. No formal scoring required at this step — qualitative advisory. |
| Expected Output | Written advisory opinion (email or memo) to Node Owner. For T4: co-signature on Gate G1-A Decision Record. |
| Evidence Required | Advisory email/memo from vCISO to Node Owner (retained in GW project folder). Co-signature on Gate G1-A Decision Record for T4. |
| Approval Required | vCISO is the approver / co-approver at this step. No further approval required for the advisory itself. |
| Acceptance Criteria | Advisory opinion submitted before Gate G1-A is signed. Opinion addresses each of the 5 review items. For T4: co-signature present on gate record. |
| Related Risk | All T3/T4 phase risks; ECON-01; CHAIN-FATAL-01; BRIDGE-01; WALLET-01 |
| Related Control | Independent risk review at high-risk engagements — compensating control for AM/NO commercial incentive bias |
| Related Policy / Standard Clause | POL-003 §2 (T3/T4 tier — vCISO mandatory); POL-001 §5.5 (risk-proportionate governance) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-1-Assessment/ (advisory email exported as PDF) |
| Audit Relevance | For T3/T4 engagements, absence of vCISO advisory is a control failure. Auditors will verify that vCISO review preceded Gate G1-A sign-off. |
| Notes / Exceptions | Track B only — if client is also performing their own security assessment, request a copy and note whether their assessment identifies any additional risks not captured in the C/B/P worksheet. |

# Phase 2: Proposal

| PRE-SALES | Track A + Track B — Track B requires explicit client acknowledgement of security scope (P2-AM-003) |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 2 |
| --- | --- |
| Phase Name | Proposal |
| Phase Objective | Produce a commercial and technical proposal that accurately represents the scope, security deliverables, timeline, and risk profile of the engagement. Ensure the client acknowledges audit requirements, security effort, and attribution rules before MSA negotiation begins. |
| Entry Criteria | Gate G1-A signed (Phase 1 complete) No open HS conditions, or conditions documented with approved escalation plan Composite Risk Score documented |
| Exit Criteria | Proposal document complete with security section Security deliverables section included and priced Attribution rules documented Residual risk acceptance path defined Client has acknowledged (Track B: in writing) security scope and audit requirements |
| Key Phase Risks | ECON-01 — Security effort not priced into proposal; client expects security "for free" REPUT-01 — Attribution agreed informally without legal review Scope creep risk if security deliverables are not explicitly bounded in proposal P5 — Audit requirement not budgeted (→ HS-03 pre-trigger if client accepts proposal without audit budget) |
| Key Control Objectives | Security section mandatory in every proposal for T2+ engagements Explicit line item for security effort (threat model, code review, external audit if required) Attribution rules reviewed by Node Owner or legal before proposal sent vCISO review of security section for T3/T4 proposals |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — Track B requires explicit client acknowledgement of security scope (P2-AM-003) |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-2-Proposal/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-02/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P2-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx Example: ACME-BRIDGE-P1-AM-001-v1.0-20260310-APPROVED.docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| AM | Account Manager | A | Owns proposal; ensures security section is included; sends to client | Approves proposal for submission (T1/T2); co-approval with NO for T3/T4 |
| NO | Node Owner | A | Approves commercial terms; ensures attribution and risk acceptance path defined | Must approve T3/T4 proposals before submission; reviews T1/T2 |
| TL | Technical Lead | R | Authors technical scope; provides effort estimate for security deliverables | Signs off technical scope section |
| vCISO | vCISO | C | Reviews security section for T3/T4; confirms audit requirement and threat model effort | Must approve security section for T3/T4 |
| SE | Sales Engineer | C | Supports technical scoping and client-facing technical communication | N/A |

## 3. Role-Based Checklist

| P2-AM-001 Draft proposal with mandatory security section [TRACK A + B] |  |
| --- | --- |
| Step ID | P2-AM-001 |
| Phase | Phase 2 — Proposal |
| Role | Account Manager (AM) |
| Control Objective | Ensure every proposal includes a defined security scope, preventing the client from contracting for delivery without understanding security obligations. |
| Action | Draft proposal with mandatory security section |
| Detailed Instruction | Produce proposal document. The proposal MUST include a dedicated Security Deliverables section covering: 1. Threat modelling commitment (effort estimate, when, who reviews): required for all T2+ engagements. 2. Internal code review commitment (minimum 2 reviewers, TL as one reviewer for smart contracts). 3. External audit: if P3 ≥ 3 (TVL > $1M) or protocol is DeFi/bridge — state explicitly whether audit is included in scope. If included, estimate cost and provider type (Big 4, specialist Web3 firm). If not included, state the residual risk and require written client acknowledgement. 4. Testnet-first deployment commitment (Step 8 gate). 5. Post-deployment monitoring: who is responsible, for how long, and what triggers escalation. Do NOT use generic language such as "we follow best practices" or "security will be considered." Each item must be specific, time-bounded, and tied to a named deliverable. Include: Public attribution rules — will Protofire name the client? Will the client name Protofire? Agreed in proposal, confirmed in MSA. |
| Required Input | Assessment Brief (P1-AM-001); C/B/P Score (P1-AM-002); Technical scope input from TL (P2-TL-001). |
| Method / Calculation / Assessment | Proposal template with mandatory security section. Security section reviewed against STD-101 Steps 5–9 control requirements to ensure all required deliverables are mentioned. |
| Expected Output | Proposal document with security section completed, all 5 security items addressed, attribution rules defined. |
| Evidence Required | Proposal document (versioned). Internal approval email from Node Owner. For T3/T4: vCISO review email/memo. |
| Approval Required | Node Owner reviews before submission for T2+. vCISO must review security section for T3/T4. |
| Acceptance Criteria | Security section present with all 5 items addressed. Audit requirement explicitly stated (included or excluded with risk note). No generic language. Attribution rules defined. |
| Related Risk | ECON-01 (unpriced security effort); REPUT-01 (attribution); P5 (audit not budgeted) |
| Related Control | Security scope in proposal — ensures client awareness before contractual commitment |
| Related Policy / Standard Clause | POL-001 §5.2; STD-101 Step 2 Preventive Controls; POL-002 §3 (security requirements that must be delivered) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-2-Proposal/P2-AM-001-Proposal-v1.0-[DATE].docx |
| Audit Relevance | Auditors verify that security obligations were defined in the proposal before MSA, not added retroactively. Proposal is evidence that client was informed of security scope at earliest opportunity. |
| Notes / Exceptions | Track B only: The proposal security section should be co-reviewed with the client technical contact where possible. Document the review meeting in meeting notes (P2-AM-003). |

| P2-TL-001 Provide security effort estimate and technical scope [TRACK A + B] |  |
| --- | --- |
| Step ID | P2-TL-001 |
| Phase | Phase 2 — Proposal |
| Role | Technical Lead (TL) |
| Control Objective | Ensure security effort is accurately estimated and that the proposal reflects realistic delivery requirements for the protocol type. |
| Action | Provide security effort estimate and technical scope |
| Detailed Instruction | Based on the protocol class from Assessment (P1-AM-001), provide: 1. Threat model effort: estimate person-days for a threat model at Phase 5. For DeFi/bridge: minimum 3 days TL + 1 day vCISO review. For dApp: minimum 1.5 days TL. For standard Web3: minimum 1 day. 2. Internal code review estimate: minimum 0.5 person-days per 1,000 lines of security-critical smart contract code. State minimum reviewer count (always ≥ 2). 3. External audit scope: if protocol is DeFi/bridge or TVL > $1M, estimate cost range for external audit (typically $15K–$80K for specialist Web3 firm depending on complexity and line count). State: "External audit is required per STD-101 Step 8 gate criteria if TVL > USD 1,000,000." 4. State whether the Protofire team has directly relevant domain expertise (P2 scoring input). If P2 = 3 or 4, recommend staffing plan. 5. Estimate gas optimization and gas failure testing effort if protocol involves on-chain execution. |
| Required Input | Assessment Brief; Protocol class identification from Phase 1. |
| Method / Calculation / Assessment | Expert estimation based on protocol class, estimated complexity, and STD-101 minimum control requirements. Use historical project data where available. |
| Expected Output | Written security effort estimate (memo or spreadsheet) with line-item breakdown per security deliverable. Signed by TL. |
| Evidence Required | Security effort estimate document/spreadsheet (versioned, dated, signed by TL). Included in or attached to proposal. |
| Approval Required | Node Owner reviews effort estimates to confirm they are within commercial feasibility before inclusion in proposal. |
| Acceptance Criteria | All 5 security effort items addressed. For DeFi/bridge: external audit cost range stated. P2 assessment documented. Estimates are in person-days, not vague qualitative statements. |
| Related Risk | P1 (technical complexity); P2 (team capability); P5 (audit requirement) |
| Related Control | Accurate security effort estimation — prevents underfunded security delivery |
| Related Policy / Standard Clause | POL-002 §3 (web3 security requirements); POL-006 §2 (testing requirements by step); STD-101 Steps 5, 6, 8 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-2-Proposal/P2-TL-001-SecurityEstimate-v1.0-[DATE].xlsx |
| Audit Relevance | Effort estimate is evidence that security was resourced as a planned activity, not an afterthought. Auditors compare proposal estimates to actual time recorded. |
| Notes / Exceptions | If the TL providing the estimate will not be the delivery TL, note the dependency. A change of TL between Proposal and Kickoff requires a re-assessment of P2 (team capability sub-score). |

| P2-AM-003 [TRACK B ONLY] Obtain client written acknowledgement of security scope [TRACK B] |  |
| --- | --- |
| Step ID | P2-AM-003 |
| Phase | Phase 2 — Proposal |
| Role | Account Manager (AM) |
| Control Objective | For Track B engagements, obtain client acknowledgement of security scope and audit requirements before MSA, ensuring informed consent and preventing post-contract disputes. |
| Action | [TRACK B ONLY] Obtain client written acknowledgement of security scope |
| Detailed Instruction | For Track B engagements only. After proposal submission, arrange a proposal walk-through meeting with the client. During or after the meeting: 1. Explicitly walk the client through the Security Deliverables section. 2. Confirm client understanding that: (a) threat model is a delivery requirement; (b) external audit is required if TVL > $1M (and if not included in scope, client carries that residual risk); (c) testnet-first deployment is mandatory; (d) two-person rule applies at production deployment. 3. Obtain written acknowledgement from client. Acceptable forms: email from client confirming they have reviewed the security section; co-signed cover page of proposal marked "Security scope acknowledged"; meeting notes recording client acknowledgement signed by both parties. 4. If client disputes any security requirement: escalate to Node Owner and vCISO before proceeding. Do not agree to remove mandatory security controls (STD-101 minimum requirements) without vCISO written approval. |
| Required Input | Proposal document (P2-AM-001); meeting invitation or call record. |
| Method / Calculation / Assessment | Meeting or written exchange. Acknowledgement documented in writing from client. |
| Expected Output | Client written acknowledgement of security scope (email, signed document, or meeting minutes with client signature). |
| Evidence Required | Client acknowledgement email (exported as PDF and saved to GW). Or: signed meeting minutes with both parties recorded. Date and client signatory name must be visible. |
| Approval Required | N/A — AM owns this step. Node Owner is notified if client disputes any security requirement. |
| Acceptance Criteria | Written acknowledgement exists from a named client representative. Document is dated. Acknowledgement covers: threat model, audit requirement, testnet-first, two-person rule. Any client objection to a security requirement is escalated (not silently removed). |
| Related Risk | Scope creep (client disputes security deliverables post-MSA); P5 (client refuses audit post-contract) |
| Related Control | Client informed consent for security scope — reduces post-contract disputes |
| Related Policy / Standard Clause | STD-101 Step 2 (Proposal — client acknowledgement requirement for Track B); POL-001 §5.2 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-2-Proposal/P2-AM-003-ClientAck-v1.0-[DATE].pdf |
| Audit Relevance | Track B audit evidence must show that client was aware of security obligations before signing MSA. Absence of client acknowledgement is a control gap for Track B. |
| Notes / Exceptions | TRACK B ONLY. Track A does not require this step. For Track A, the proposal security section is internal governance only. |

# Phase 3: MSA / Contract

| PRE-SALES | Track A + Track B — Track B requires client co-signing on specific MSA clauses as noted in P3-AM-002 |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 3 |
| --- | --- |
| Phase Name | MSA / Contract |
| Phase Objective | Execute a legally binding Master Services Agreement before any delivery activity commences. Confirm contractual protections (IP, liability cap, confidentiality, security annexe) are in place. Record the Go/No-Go gate that separates Sales from Delivery. HS-02 (no MSA) is the most operationally critical Hard Stop — Phase 4 cannot begin without a signed MSA. |
| Entry Criteria | Gate G1-A signed (Phase 1 complete) Proposal submitted and client has responded Client has not yet received any delivery work product |
| Exit Criteria | Signed MSA with all required clauses confirmed Security annexe or security deliverables schedule referenced in MSA Payment schedule confirmed in Finance system Gate G2 signed by Node Owner (and Legal/DoE for T3/T4) HS-02 is formally CLEAR |
| Key Phase Risks | HS-02 — Delivery commences without signed MSA (most frequently seen control failure) B3 — Liability cap absent or inadequate B1/B2 — Payment terms inadequate or arrears risk not addressed Legal-02 — MSA implies fiduciary duty or custody obligation (DeFi/wallet protocols) |
| Key Control Objectives | HS-02 Hard Stop: Phase 4 gate is blocked until signed MSA is recorded IP assignment clause mandatory in all MSAs Liability cap clause mandatory Security annexe reference mandatory Legal review required for T3/T4 |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — Track B requires client co-signing on specific MSA clauses as noted in P3-AM-002 |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-3-MSA/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-03/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P3-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx Example: ACME-BRIDGE-P1-AM-001-v1.0-20260310-APPROVED.docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| NO | Node Owner | A | Accountable for MSA execution; confirms all required clauses are present; signs Gate G2 | Signs Gate G2 for all engagements |
| AM | Account Manager | R | Manages client negotiation; coordinates legal; ensures MSA is signed before Phase 4 | Confirms payment terms to Finance |
| vCISO | vCISO | C | Reviews MSA for implied fiduciary/custody clauses (LEGAL-02 risk); T3/T4 mandatory review | Must co-sign Gate G2 for T3/T4 |
| FIN | Finance/Billing | I | Confirms payment schedule is recorded in billing system; sets arrears monitoring (B2/HS-05) | N/A |
| PM | Project Manager | C | Reviews scope definition in MSA for alignment with project RACI and timeline | N/A |

## 3. Role-Based Checklist

| P3-AM-001 Verify MSA contains all mandatory contractual protections [TRACK A + B] |  |
| --- | --- |
| Step ID | P3-AM-001 |
| Phase | Phase 3 — MSA / Contract |
| Role | Account Manager (AM) |
| Control Objective | Ensure that all mandatory MSA clauses are present before the agreement is presented for signature, preventing structurally deficient contracts. |
| Action | Verify MSA contains all mandatory contractual protections |
| Detailed Instruction | Before presenting the MSA for signature, perform a clause-level review against the following mandatory checklist: Mandatory Clauses (B3 = Score 1 requires ALL four): [ ] IP Assignment: All IP created during the engagement is assigned to the client upon payment, or retained by Protofire if agreed — state which. [ ] Liability Cap (LoL): Protofire liability is explicitly capped. Recommended: cap at total contract value or 12 months of fees. If cap is absent, P4 scores 4 (no cap = max project risk). [ ] Confidentiality / NDA: Client information and Protofire proprietary methods are mutually protected. [ ] Payment Schedule: Milestone or monthly schedule explicitly defined with amounts and dates. Mandatory References (for T2+ and all Web3 engagements): [ ] Security Annexe or Security Deliverables Schedule referenced (by name or as attachment). The annexe must include the items from the Proposal security section. [ ] External Audit clause: if TVL > $1M, MSA must acknowledge the audit requirement and define who funds it. [ ] Attribution clause: public naming of Protofire and/or client as agreed in Proposal. For T3/T4 additionally: [ ] Legal review completed (evidence: legal email or memo in project folder). [ ] LEGAL-02 review: if the protocol is a DeFi/bridge/wallet, confirm MSA does not imply Protofire takes custody or provides financial advice. vCISO to review (P3-vCISO-001). |
| Required Input | MSA draft from legal; Proposal document (for security scope comparison); C/B/P scoring (for clause adequacy check against B3). |
| Method / Calculation / Assessment | Clause-level checklist review. Each item marked PRESENT / ABSENT / NOT APPLICABLE with page/section reference. |
| Expected Output | MSA Clause Verification Checklist completed, all mandatory items PRESENT or N/A with documented justification. |
| Evidence Required | MSA Clause Verification Checklist (signed by AM). Executed MSA (fully signed by both parties). Legal review memo (T3/T4). |
| Approval Required | Node Owner must review and confirm all mandatory clauses are present before MSA is signed. Legal review required for T3/T4. |
| Acceptance Criteria | All 4 mandatory clauses present. Security annexe referenced. Payment schedule defined. No clause is marked ABSENT without a documented justification approved by Node Owner and vCISO. |
| Related Risk | B3 (contractual protections); LEGAL-02 (implied fiduciary); P4 (liability exposure) |
| Related Control | MSA clause verification — prevents structurally deficient contracts |
| Related Policy / Standard Clause | POL-001 §5.3 (HS-02); STD-101 Step 3 Preventive Controls; POL-008 (MSA retention 7 years) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-3-MSA/P3-AM-001-MSA-ClauseCheck-v1.0-[DATE].docx Executed MSA: /[Client]/[Project]/Legal/[CLIENT]-MSA-v[N]-EXECUTED-[DATE].pdf |
| Audit Relevance | Executed MSA is a primary legal and governance artifact. Auditors verify MSA is signed, dated, and contains all required clauses. Absence of liability cap is a High-severity finding. |
| Notes / Exceptions | If client insists on removing liability cap, escalate to Node Owner + Legal. Do not proceed without written approval from Node Owner. Update P4 score to 4 and re-run composite score. |

| P3-NO-001 Gate G2: MSA execution confirmation and Phase 3 → Phase 4 authorization [TRACK A + B] |  |
| --- | --- |
| Step ID | P3-NO-001 |
| Phase | Phase 3 — MSA / Contract |
| Role | Node Owner (NO) |
| Control Objective | Gate G2: Confirm that the MSA is executed and that all commercial and security preconditions for delivery commencement are satisfied. |
| Action | Gate G2: MSA execution confirmation and Phase 3 → Phase 4 authorization |
| Detailed Instruction | Review MSA Clause Verification Checklist (P3-AM-001). Confirm: 1. Executed MSA is in the project folder (both signatures present, dated). 2. All mandatory clauses are PRESENT. 3. Security annexe is referenced. 4. Payment schedule is confirmed in the Finance system (verify with FIN/Billing). 5. No TRIGGERED Hard Stop conditions remain unresolved. 6. For T3/T4: vCISO and Legal reviews are documented. For Track B specifically: confirm that the client contact who signed the MSA has the authority to bind the client entity (check against company records or ask for confirmation of signatory authority). Sign Gate G2 Decision Record. This record is the authorization for Phase 4 (Kickoff) to commence. Without this signed record, Phase 4 is blocked per HS-02. |
| Required Input | Executed MSA; MSA Clause Verification Checklist; Finance payment schedule confirmation; vCISO review (T3/T4). |
| Method / Calculation / Assessment | Review and sign-off. If any item is missing: return to AM. Gate G2 cannot be signed with open items. |
| Expected Output | Gate G2 Decision Record: signed by Node Owner (and vCISO for T3/T4), dated, Go/No-Go/Go-with-Conditions. |
| Evidence Required | Gate G2 Decision Record (signed). Executed MSA (in Legal subfolder). Finance payment schedule confirmation (email or system screenshot). |
| Approval Required | Node Owner (all tiers). vCISO co-sign for T3/T4. |
| Acceptance Criteria | Gate G2 Decision Record is signed, dated, and specifies Go. Executed MSA is saved and versioned. Finance confirmation is documented. No open HS conditions. |
| Related Risk | HS-02 (no signed MSA); B3 (contractual protections) |
| Related Control | Gate G2 — MSA execution gate; HS-02 enforcement |
| Related Policy / Standard Clause | POL-001 §5.3 (HS-02); STD-101 Step 3 Gate column; POL-001 §5.2 (Gate Criteria) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-3-MSA/P3-NO-001-Gate-G2-Decision-v1.0-[DATE].docx |
| Audit Relevance | Gate G2 is the Phase 3 exit gate. Auditors verify that the Gate G2 timestamp precedes all Phase 4 activity timestamps. Absence of Gate G2 record with Phase 4 activity is a Critical finding (HS-02 breach). |
| Notes / Exceptions | Track B: client co-signing authority should be verified. Request proof of signatory authority for contract values > $500K. |

| P3-FIN-001 Record payment schedule and activate arrears monitoring [TRACK A + B] |  |
| --- | --- |
| Step ID | P3-FIN-001 |
| Phase | Phase 3 — MSA / Contract |
| Role | Finance / Billing (FIN) |
| Control Objective | Activate payment arrears monitoring immediately upon MSA execution to ensure HS-05 (60-day arrears) trigger is detected in time. |
| Action | Record payment schedule and activate arrears monitoring |
| Detailed Instruction | Upon receiving confirmation that MSA is executed (Gate G2 signed): 1. Enter the payment schedule into the billing system (milestone amounts, dates, payment method). 2. Set up automated or calendar-based 30-day alert (Amber) and 60-day alert (Red/HS-05) for each payment milestone. 3. Confirm invoice delivery method with client (email address, billing contact, purchase order requirement if applicable). 4. Notify AM and Node Owner via email confirming payment schedule is active and monitoring is set. 5. Record client billing contact name and email in project folder. |
| Required Input | Executed MSA (payment schedule section); client billing contact information. |
| Method / Calculation / Assessment | Entry into billing system. Calendar/system alerts configured. Confirmation email sent to AM and NO. |
| Expected Output | Payment schedule in billing system. Alerts configured. Confirmation email sent. |
| Evidence Required | Screenshot of billing system entry (payment schedule). Calendar alert configuration screenshot. Confirmation email (PDF export) to AM/NO. |
| Approval Required | N/A — Finance executes this step; Node Owner receives notification. |
| Acceptance Criteria | Payment schedule in system matches MSA. 30-day and 60-day alerts configured for each milestone. Confirmation email sent within 2 business days of Gate G2 sign-off. |
| Related Risk | B2 (payment history); HS-05 (arrears > 60 days triggers stop-work) |
| Related Control | Arrears monitoring — early detection of payment risk |
| Related Policy / Standard Clause | POL-003 §2 (B2 sub-score monitoring); STD-101 Step 3 cross-step control; KRI-06 in POL-010 §3 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-3-MSA/P3-FIN-001-PaymentSchedule-[DATE].pdf |
| Audit Relevance | Auditors verify that payment monitoring was activated at contract execution, not retroactively after arrears arose. System screenshot with date is required. |
| Notes / Exceptions | If payment is deferred (B1=4) or the client has prior arrears (B2=3), escalate to Node Owner immediately and set 15-day (not 30-day) Amber threshold. |

# Phase 4: Kickoff

| DELIVERY | Track A + Track B — Track B requires client participation in kickoff meeting and client RACI acknowledgement (P4-PM-003) |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 4 |
| --- | --- |
| Phase Name | Kickoff |
| Phase Objective | Formally initiate the delivery phase. Assign named individuals to all RACI roles, set up the project environment with security baseline active, initiate the Project Security Framework document, confirm budget and resources, and establish the evidence collection structure. Gate G3 closes this phase. |
| Entry Criteria | Gate G2 signed (Phase 3 complete) Executed MSA in project folder Payment schedule active in Finance system No open HS conditions |
| Exit Criteria | All RACI roles populated with named individuals Project environment set up with security baseline (branch protection, secret scanning, SCA) Project Security Framework document initiated (draft version) Gate G3 signed by Node Owner and PM Budget confirmed with Finance Kickoff meeting conducted and minutes recorded |
| Key Phase Risks | Staffing risk — named team members not confirmed or unavailable Environment misconfiguration — security baseline not activated at project start SoD breach — Node Owner acting as PM without DoE co-sign mechanism established Resource Manager not aligned on allocation |
| Key Control Objectives | RACI must name individuals (not just roles) before Phase 5 begins Security baseline configuration verified by vCISO before Phase 5 gate SoD check: if NO = PM, DoE co-sign mechanism for future gates must be established at kickoff Project Security Framework (PSF) initiated — minimum: protocol class, TVL, upgrade/pause intent |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — Track B requires client participation in kickoff meeting and client RACI acknowledgement (P4-PM-003) |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-4-Kickoff/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-04/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P4-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx Example: ACME-BRIDGE-P1-AM-001-v1.0-20260310-APPROVED.docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| NO | Node Owner | A | Accountable for team assignment; approves RACI; signs Gate G3 | Signs Gate G3; must establish DoE co-sign mechanism if also acting as PM |
| PM | Project Manager | R | Coordinates kickoff meeting; populates RACI; manages project system setup | Co-signs Gate G3 |
| TL | Technical Lead | C | Confirms technical environment setup; reviews security baseline configuration | Signs off security baseline (P4-TL-001) |
| RM | Resource Manager | A | Confirms named resources are allocated; staffing confirmed for full delivery scope | Confirms resource allocation in writing |
| Dev | Developer | R | Sets up development environment per security baseline; confirms tools are operational | N/A |
| DevOps | DevOps Engineer | R | Configures CI/CD pipeline with security gate; confirms secret scanning active | N/A |
| vCISO | vCISO | C | Reviews RACI for SoD compliance; reviews PSF initial version; reviews security baseline config | Must flag SoD violations before Gate G3 |
| AM | Account Manager | I | Informed of kickoff; confirms client billing contact is active (Track B: attends kickoff) | N/A |

## 3. Role-Based Checklist

| P4-PM-001 Populate RACI-001 with named individuals for this project [TRACK A + B] |  |
| --- | --- |
| Step ID | P4-PM-001 |
| Phase | Phase 4 — Kickoff |
| Role | Project Manager (PM) |
| Control Objective | Ensure every project role is assigned to a named individual before delivery begins, preventing unaccountable execution and untraceable decisions. |
| Action | Populate RACI-001 with named individuals for this project |
| Detailed Instruction | Using RACI-001 as the template, populate all role fields with named individuals: Required minimum roles to be named before Gate G3: NO: Node Owner (name + email) PM: Project Manager / Scrum Master (may be same as NO — flag SoD implication) AM: Account Manager (may be same as NO — flag SoD implication) TL: Technical Lead / Architect (must be named; cannot be vacant) Dev: At least one named Developer QA: At least one named QA Engineer (can be same as Dev for T1, but for T2+: must be a different person) DevOps: Named (can be same as Dev for T1; for T2+: should be distinct) vCISO: Always Aleksey Lekontsev / Altoros (as confirmed; do not substitute) For Track B additionally: CUST: Name the client Product Owner or project contact For T3/T4 additionally: fCTO: Field CTO named (or documented why not required for this engagement) For any role where NO, PM, and AM are the same person: Document this explicitly in the RACI with the note: "Node Owner acting in multi-role capacity — DoE co-sign required at all T2+ gates per POL-004 §2.4." Save RACI as version-controlled document in GW project folder. |
| Required Input | RACI-001 template; resource allocation from RM (P4-RM-001); C/B/P Score (to determine T-tier and role requirements). |
| Method / Calculation / Assessment | Fill RACI-001 template with named individuals. Verify each required role has a name before saving. Verify QA and Dev are different people for T2+. |
| Expected Output | RACI-001 project instance — all required roles named, version 1.0, dated, signed by PM and NO. |
| Evidence Required | RACI-001 project instance (named, signed, version-controlled in GW). If NO = PM: explicit SoD notation present. |
| Approval Required | Node Owner signs RACI instance. vCISO must review SoD compliance (see P4-vCISO-001). |
| Acceptance Criteria | All required roles named (no "TBD" for mandatory roles). QA ≠ Dev for T2+. vCISO is not substituted. SoD multi-role notation present if applicable. Version number and date visible. |
| Related Risk | SoD breach; staffing risk; unaccountable gate decisions |
| Related Control | Named RACI — establishes individual accountability for all governance actions |
| Related Policy / Standard Clause | RACI-001 (Unified RACI); POL-004 §2.4 (SoD requirements); POL-001 §5.4 (Node Owner multi-role) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-4-Kickoff/P4-PM-001-RACI-ProjectInstance-v1.0-[DATE].docx |
| Audit Relevance | Named RACI is the foundation of all accountability tracing. Auditors will cross-reference gate signatures against RACI. Any gate signed by a person not named in RACI requires explanation. |
| Notes / Exceptions | If a named team member leaves the project mid-delivery, RACI must be updated within 2 business days and versioned (v1.1, v1.2, etc.). Gate sign-offs after a personnel change must reference the updated RACI version. |

| P4-TL-001 Configure and verify project security baseline [TRACK A + B] |  |
| --- | --- |
| Step ID | P4-TL-001 |
| Phase | Phase 4 — Kickoff |
| Role | Technical Lead (TL) |
| Control Objective | Ensure security controls are active in the development environment from day one of delivery, preventing security baseline gaps that are costly to remediate later. |
| Action | Configure and verify project security baseline |
| Detailed Instruction | Set up and verify the following security baseline before the first development commit is made: 1. Source code repository: [ ] Branch protection enabled on main/master: require PR review (minimum 2 reviewers for T2+) [ ] Force-push disabled on protected branches [ ] Repository is private (no public repositories for client delivery work) [ ] Secret scanning enabled (GitHub/GitLab native or equivalent: TruffleHog, GitGuardian) [ ] Dependency vulnerability scanning enabled (Dependabot, Snyk, or equivalent) 2. CI/CD pipeline: [ ] SAST (Static Analysis Security Testing) integrated and running on every PR: Slither/Mythril for Solidity; SonarQube or equivalent for other languages [ ] CI/CD gate configured: Critical and High SAST findings block PR merge [ ] No credentials, private keys, or secrets in any CI/CD environment variables in plaintext — use secrets vault 3. Secrets and key management: [ ] Local developer .env files are git-ignored [ ] A secrets vault (HashiCorp Vault, AWS Secrets Manager, or equivalent) is provisioned for sensitive configuration [ ] All team members briefed on no-hard-coded-secrets policy 4. Documentation: [ ] README includes security setup instructions [ ] Security contact (vCISO) is documented in project README Document each item as CONFIGURED / NOT REQUIRED / NOT YET AVAILABLE (with plan). No item may be left blank. |
| Required Input | Project repository URL; CI/CD platform; access to repository settings. |
| Method / Calculation / Assessment | Configuration and verification. Each item verified by TL. DevOps co-verifies CI/CD items. |
| Expected Output | Security Baseline Configuration Checklist (completed, signed by TL and DevOps). |
| Evidence Required | Security Baseline Configuration Checklist (signed, dated). Screenshots of: branch protection settings; SAST integration status; secret scanning enabled. CI/CD pipeline configuration file (e.g., .github/workflows/ or .gitlab-ci.yml) committed to repository. |
| Approval Required | vCISO must review and acknowledge the Security Baseline Checklist before Gate G3 is signed. |
| Acceptance Criteria | All items CONFIGURED or NOT REQUIRED with justification. No Critical or High SAST gate is disabled. Secret scanning is active. vCISO acknowledgement received. Screenshots are dated. |
| Related Risk | SEC-CRIT-01 (critical vuln from early in development); hard-coded secrets; unauthorized commits |
| Related Control | Security baseline configuration — mandatory preventive control from Phase 4 |
| Related Policy / Standard Clause | POL-002 §3.1 (SAST at CI/CD gate); POL-002 §3.3 (no hard-coded credentials); STD-101 Step 4 Preventive Controls |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-4-Kickoff/P4-TL-001-SecurityBaseline-v1.0-[DATE].docx Screenshots: /[Client]/[Project]/GRC/Phase-4-Kickoff/evidence/security-baseline-screenshots/ |
| Audit Relevance | Security baseline is audited at Gate G3 and re-verified at Gate G5. Auditors check that SAST was active from the first PR, not added after code was already committed. |
| Notes / Exceptions | If SAST tooling is not immediately available (e.g., waiting for license provisioning), document the gap, set a deadline of 3 business days, and do not push any security-critical contract code until SAST is active. |

| P4-PM-002 Initiate Project Security Framework (PSF) document [TRACK A + B] |  |
| --- | --- |
| Step ID | P4-PM-002 |
| Phase | Phase 4 — Kickoff |
| Role | Project Manager (PM) |
| Control Objective | Initiate the Project Security Framework to establish security governance context for the engagement before technical work begins. |
| Action | Initiate Project Security Framework (PSF) document |
| Detailed Instruction | Create the PSF document in the GW project folder. At Kickoff, the PSF must include at minimum: 1. Protocol Class: (DeFi / bridge / wallet / dApp / Web3 standard / non-Web3) 2. TVL/Value at Risk estimate: (from Assessment; state if unknown with default applied) 3. Upgrade/Pause/Kill-switch intent: - Does the protocol have an upgrade mechanism? (yes / no / planned but not scoped) - Does the protocol have a pause function? (yes / no / planned) - If neither: document the irreversibility acceptance (who accepts this risk, when) 4. Public attribution rules: (from Proposal/MSA) 5. Residual risk acceptance path: (who accepts remaining risk post-deployment — client, Protofire, or shared) 6. Key ownership intent: (client holds keys / Protofire holds keys during delivery then transfers / shared multisig) 7. Monitoring intent: (who monitors post-deployment; what tool; what triggers escalation) 8. Risk tier (T1–T4) and composite score (from Phase 1). 9. External audit status: (required Y/N; planned Y/N; provider if known). 10. Incident response contact: (vCISO name + contact for any security event). PSF is a living document — it will be updated at each gate. Version v0.1 at Kickoff is the baseline. |
| Required Input | Assessment Brief (P1-AM-001); C/B/P Score (P1-AM-002); Proposal (P2-AM-001); MSA security annexe. |
| Method / Calculation / Assessment | Document creation using PSF template. Each field completed or marked "TBD — to be resolved by Phase 5 gate." No field may be blank without a deadline for resolution. |
| Expected Output | PSF v0.1 with all 10 fields completed or noted as TBD with resolution deadline. |
| Evidence Required | PSF v0.1 document (dated, signed by PM and TL). Version-controlled in GW project folder. |
| Approval Required | TL reviews and co-signs. vCISO reviews for T3/T4. |
| Acceptance Criteria | PSF exists, is version-controlled, all 10 fields are completed or TBD with deadline. Key ownership intent is not blank for any engagement involving on-chain operations. |
| Related Risk | CHAIN-FATAL-01; WALLET-01; HS-06; HS-07 |
| Related Control | Project Security Framework initiation — establishes security governance baseline for delivery |
| Related Policy / Standard Clause | STD-101 Step 4 (Project Security Framework init); POL-002 §3.5 (web3 requirements); POL-008 §2 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-4-Kickoff/P4-PM-002-PSF-v0.1-[DATE].docx |
| Audit Relevance | PSF is traced through all subsequent gates. Auditors verify that key ownership intent was documented at Phase 4, not added retroactively before Phase 9. |
| Notes / Exceptions | If the client is Track B: share the PSF with the client contact and obtain their acknowledgement that key ownership intent is correctly recorded. Save the client acknowledgement email in the GW folder. |

| P4-NO-001 Gate G3: Kickoff completion confirmation — authorize Phase 5 start [TRACK A + B] |  |
| --- | --- |
| Step ID | P4-NO-001 |
| Phase | Phase 4 — Kickoff |
| Role | Node Owner (NO) |
| Control Objective | Gate G3: Confirm that all kickoff prerequisites are met and that delivery can commence with full accountability structure in place. |
| Action | Gate G3: Kickoff completion confirmation — authorize Phase 5 start |
| Detailed Instruction | Review and confirm: 1. RACI-001 project instance is signed with named individuals (P4-PM-001). If NO = PM: SoD notation is present and DoE co-sign mechanism is established. 2. Security Baseline Checklist signed by TL and acknowledged by vCISO (P4-TL-001). 3. PSF v0.1 exists and is version-controlled (P4-PM-002). 4. Budget and resource allocation confirmed by RM. 5. Kickoff meeting conducted and minutes recorded (P4-PM-003). 6. Payment schedule confirmed active in Finance system (P3-FIN-001 — verify is still active). 7. No open HS conditions. For Track B additionally: 8. Client attended kickoff (or Track B equivalent was performed) and client RACI role is named in RACI project instance. Sign Gate G3 Decision Record. |
| Required Input | RACI-001 instance; Security Baseline Checklist; PSF v0.1; RM resource confirmation; kickoff meeting minutes; payment schedule confirmation. |
| Method / Calculation / Assessment | Review and sign-off of submitted documents. |
| Expected Output | Gate G3 Decision Record: signed by Node Owner and PM (and DoE if NO = PM), dated. |
| Evidence Required | Gate G3 Decision Record (signed). All prerequisite documents referenced and accessible in GW project folder. |
| Approval Required | Node Owner + PM. If NO = PM: Director of Engineering must co-sign Gate G3. |
| Acceptance Criteria | Gate record signed, dated. All 7 (or 8 for Track B) prerequisites confirmed. No open items without documented resolution plan and deadline. |
| Related Risk | SoD breach; staffing risk; security baseline gap |
| Related Control | Gate G3 — delivery authorization gate |
| Related Policy / Standard Clause | POL-001 §5.2; STD-101 Step 4 Gate column; RACI-001 §4 (Kickoff section) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-4-Kickoff/P4-NO-001-Gate-G3-Decision-v1.0-[DATE].docx |
| Audit Relevance | Gate G3 is the Phase 4 exit gate. Auditors verify that all Phase 5 activity timestamps are later than Gate G3 sign-off. If NO = PM, auditors will specifically look for DoE co-signature. |
| Notes / Exceptions | Track B: if client was unable to attend kickoff, the Track B client acknowledgement step must be completed within 5 business days of Gate G3 sign-off. |

| P4-PM-003 [TRACK B ONLY] Conduct client-facing kickoff and confirm client RACI [TRACK B] |  |
| --- | --- |
| Step ID | P4-PM-003 |
| Phase | Phase 4 — Kickoff |
| Role | Project Manager (PM) |
| Control Objective | For Track B engagements, formally introduce the governance framework to the client and confirm their role in the delivery RACI. |
| Action | [TRACK B ONLY] Conduct client-facing kickoff and confirm client RACI |
| Detailed Instruction | For Track B only. Conduct or arrange a kickoff meeting that includes the client contact (Product Owner or equivalent). In the meeting: 1. Present the project RACI and confirm the client Product Owner (CUST role) understands their responsibilities: Track B gate co-approvals; accepting risk at relevant gates; providing timely input at defined steps. 2. Confirm client access to relevant project tooling (e.g., GitHub repo read access, project management tool, shared GW folder). 3. Confirm client security contact (who to contact for security concerns). 4. Walk through the delivery timeline and gate schedule. 5. Confirm communication cadence and escalation path. Record kickoff meeting minutes documenting: attendees, date, decisions made, client acknowledgement of RACI. |
| Required Input | RACI-001 project instance (with CUST role named); project timeline; Phase 5–12 gate schedule. |
| Method / Calculation / Assessment | Live meeting or video call. Meeting minutes recorded in real time or within 24 hours. |
| Expected Output | Kickoff meeting minutes with: attendee list (including client name and role), decisions, client acknowledgement of RACI. |
| Evidence Required | Kickoff meeting minutes (signed by PM; client attendee named). Client email confirmation of attendance or signed minutes. Saved in GW project folder. |
| Approval Required | PM owns this step. Node Owner is notified. |
| Acceptance Criteria | Meeting minutes exist with client name and role recorded. Client RACI acknowledgement is documented. Communication cadence is agreed and recorded. |
| Related Risk | OPS-01 (responsibility creep from unclear client RACI) |
| Related Control | Client RACI introduction — establishes shared governance expectations for Track B |
| Related Policy / Standard Clause | POL-001 §5.1 (Track B engagement model); RACI-001 §4 (CUST role) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-4-Kickoff/P4-PM-003-Kickoff-Minutes-[DATE].docx |
| Audit Relevance | Track B audit evidence must show client was onboarded to governance model at kickoff, not mid-delivery. Absence of client kickoff record is a Track B control gap. |
| Notes / Exceptions | TRACK B ONLY. If client declines to participate in kickoff, document the refusal and escalate to Node Owner. Node Owner decides whether to proceed. |

# Phase 5: Discovery Phase

| DELIVERY | Track A + Track B — Track B adds client review of threat model (P5-TL-004) and client sign-off on admin matrix |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 5 |
| --- | --- |
| Phase Name | Discovery Phase |
| Phase Objective | Establish the secure technical foundation before any build commences. Threat model, admin/control matrix, multisig policy, dependency matrix, and incident response plan must all be approved before Phase 6 begins. Gate G4 enforces this. This gate prevents design-level security failures that cannot be fixed by any audit after the fact. |
| Entry Criteria | Gate G3 signed (Phase 4 complete) Named RACI in place Security baseline active in project environment PSF v0.1 in project folder |
| Exit Criteria | Threat model approved by TL + vCISO (signed) Admin/control matrix completed and stored Multisig and signer policy defined Testnet-first deployment commitment confirmed Incident response plan draft completed Dependency matrix documented (oracle/bridge/RPC with fallbacks) Gate G4 signed by TL and vCISO |
| Key Phase Risks | GOV-01 — Governance attack vector (flash-loan voting, signer collusion) not addressed in threat model ADMIN-01 — Single EOA admin without multisig (→ Gate G4 block) DEP-01 — Dependency fragility: oracle or bridge SPOF not documented LEGAL-02 — Implied fiduciary/custody role in DeFi/wallet UI not identified ECON-01 — Economic attack surface (MEV, arbitrage, griefing) not modelled |
| Key Control Objectives | Threat model must cover all 4 categories: technical, economic, governance, human failure Admin/control matrix mandatory for all on-chain protocols Multisig minimum 2-of-3 signers for production admin functions Dependency matrix must document fallback for every external dependency IRP draft before Phase 6 starts |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — Track B adds client review of threat model (P5-TL-004) and client sign-off on admin matrix |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-5-Discovery/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-05/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P5-[ROLE]-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| TL | Technical Lead | A | Leads threat model; completes admin/control matrix; defines architecture security requirements | Must co-sign Gate G4 |
| vCISO | vCISO | A | Reviews and approves threat model; checks for LEGAL-02; reviews IRP draft; co-signs Gate G4 | Must co-sign Gate G4 — Gate G4 cannot be signed without vCISO |
| Dev | Developer | R | Provides input on technical implementation feasibility; documents dependency integrations | N/A |
| BA | Business Analyst | R | Documents business requirements and maps to threat model user-facing risks | N/A |
| DevOps | DevOps | C | Documents infrastructure dependencies, RPC providers, node infra, CI/CD security config | N/A |
| fCTO | Field CTO | C | Architecture review for T3/T4; cross-chain and novel protocol expert input | Co-sign for T3/T4 architecture review |
| NO | Node Owner | I | Informed of threat model outcomes; receives IRP contact info; notified of any GOV-01/ADMIN-01 gate block | N/A |

## 3. Role-Based Checklist

| P5-TL-001 Complete threat model (all 4 categories: technical, economic, governance, human failure) [TRACK A + B] |  |
| --- | --- |
| Step ID | P5-TL-001 |
| Phase | Phase 5 — Discovery |
| Role | Technical Lead (TL) |
| Control Objective | Produce a threat model that comprehensively identifies attack vectors across all four required categories before any code is written, ensuring security by design rather than by retrofit. |
| Action | Complete threat model (all 4 categories: technical, economic, governance, human failure) |
| Detailed Instruction | Produce the threat model document covering all four mandatory categories. For each category, enumerate threats relevant to this protocol class: Category 1 — Technical Exploits: - Reentrancy (single and cross-function) - Integer overflow / underflow (even with Solidity 0.8+ — check unchecked blocks) - Access control bypass (missing modifier, tx.origin, role not initialized) - Signature replay / ECDSA malleability - Front-running / sandwich attacks on state-changing functions - Flashloan-enabled state manipulation - Storage collision (proxy patterns) - Initialization vulnerabilities (initializer can be called by anyone) Category 2 — Economic Exploits (required for DeFi/incentive protocols): - MEV extraction: sandwich, JIT liquidity, liquidation ordering - Oracle manipulation: spot price oracles, TWAP manipulation with large capital - Incentive gaming: profitable but intended (not-a-bug) extraction paths - Griefing: making protocol unusable for others at low attacker cost - Token economic: inflation/deflation attacks, reserve drain Category 3 — Governance Attacks: - Flash-loan voting (temporary token acquisition to pass proposals) - Signer collusion (multisig members coordinate maliciously) - Governance front-running (proposal front-run to influence outcome) - Emergency pause abuse (pause function used maliciously) - Upgrade attack (malicious upgrade proposed through governance) Category 4 — Human Failure: - Private key loss (no recovery mechanism) - Phishing of admin key holder - Wrong address in deployment (owner set to wrong address) - Missing timelock allowing immediate admin action - Untested pause function that fails in emergency For each threat: Rate likelihood (Low/Medium/High), impact (Low/High/Critical), and specify the mitigating control planned. Flag any threat with no mitigation as OPEN (→ must be resolved before Phase 6 gate). The threat model must reference this engagement's specific protocol class and TVL range. |
| Required Input | PSF v0.1; protocol class from Assessment; architecture diagrams (preliminary); business requirements from BA. |
| Method / Calculation / Assessment | STRIDE-inspired threat enumeration adapted for Web3. Use threat model template covering all 4 categories. TL leads with Dev input. vCISO reviews independently before signing. |
| Expected Output | Threat model document (complete): all 4 categories covered, each threat rated, mitigations listed, OPEN items flagged. |
| Evidence Required | Threat model document (signed by TL and vCISO), version-controlled. Any OPEN items tracked in project issue register. |
| Approval Required | vCISO must review and co-sign. For T3/T4: fCTO reviews architecture sections. |
| Acceptance Criteria | All 4 categories present. Each threat has: likelihood rating, impact rating, mitigation (or OPEN flag). No OPEN items from Category 1 (Technical) remain before Phase 6 gate. For DeFi/bridge: Category 2 fully completed. Sign-off by both TL and vCISO. |
| Related Risk | GOV-01; ADMIN-01; ECON-01; SEC-CRIT-01 |
| Related Control | Threat model (mandatory before build) — STD-101 Step 5 preventive control |
| Related Policy / Standard Clause | POL-002 §3.5 (threat model requirement); STD-101 Step 5 Gate criteria; POL-006 §2 (testing requires threat model as input) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-5-Discovery/P5-TL-001-ThreatModel-v1.0-[DATE].docx Repository: /docs/governance/phase-05/threat-model.md |
| Audit Relevance | Threat model is the primary design-phase security evidence. Auditors verify: (1) all 4 categories are present; (2) threats relevant to the protocol class are included; (3) vCISO co-signed; (4) document predates first Phase 6 commit. |
| Notes / Exceptions | Track B: share the threat model with the client technical contact and request their review. Client review does not replace vCISO review but may identify protocol-specific attack vectors the Protofire team was not aware of. Document client review as meeting note or email. |

| P5-TL-002 Complete admin/control matrix (pause / upgrade / drain / fee change / ownership) [TRACK A + B] |  |
| --- | --- |
| Step ID | P5-TL-002 |
| Phase | Phase 5 — Discovery |
| Role | Technical Lead (TL) |
| Control Objective | Document all privileged on-chain functions and key custody arrangements before build commences, preventing unauthorized or single-point-of-failure admin control. |
| Action | Complete admin/control matrix (pause / upgrade / drain / fee change / ownership) |
| Detailed Instruction | Create the Admin/Control Matrix document. For every privileged function in the protocol, document: Column headers: Function Name ¦ Function Type ¦ Who Can Call ¦ How (EOA / Multisig / Governance) ¦ Timelock (Y/N, duration) ¦ Number of Signers ¦ Signer Identities ¦ Revocability ¦ Fallback if Primary Unavailable Mandatory function categories to cover: 1. Pause / Emergency Stop: who can pause, how fast (must be < 1 block if critical), can anyone unpause, is there a timeout? 2. Upgrade / Proxy Admin: who can upgrade contract logic, via governance vote or direct admin call, timelock minimum? 3. Owner Transfer: who can transfer contract ownership, timelock required? 4. Drain / Withdraw: who can remove funds from protocol-controlled accounts? 5. Fee Change: who can change fees, are there caps, timelock? 6. Oracle / Price Feed Admin: who can change oracle source? 7. Role Grant/Revoke: who can add or remove admin roles? For each function, define the on-chain implementation: - If multisig: minimum 2-of-N signers, N ≥ 3 for production (per POL-004 §2.5) - If governance: minimum timelock duration (recommended: 24–72 hours for non-emergency) - If single EOA: this is an ADMIN-01 finding → must be mitigated before Gate G4 Document who the signers are (name, wallet address, hardware wallet Y/N) for all multisig arrangements. |
| Required Input | Protocol architecture; threat model (P5-TL-001); PSF v0.1. |
| Method / Calculation / Assessment | Review smart contract interfaces and architecture. Document every admin entry point. Cross-check against ADMIN-01 risk in threat model. |
| Expected Output | Admin/Control Matrix document: all admin functions documented, multisig policy defined, signer identities recorded where known. |
| Evidence Required | Admin/Control Matrix (signed by TL). Saved in GW project folder and referenced in PSF. |
| Approval Required | vCISO reviews and signs. Node Owner is informed of key custody arrangements. |
| Acceptance Criteria | All admin functions documented. No single EOA without mitigating control. Multisig minimum 2-of-3 for any production function. Timelocks documented. ADMIN-01: if single EOA is unavoidable (e.g., client requirement), document the compensating control and obtain vCISO exception. |
| Related Risk | ADMIN-01; WALLET-01; HS-07 |
| Related Control | Admin/control matrix — mandatory per STD-101 Step 5; enforces POL-004 §2.5 |
| Related Policy / Standard Clause | POL-004 §2.5 (on-chain multisig minimum 2-of-3); STD-101 Step 5 Gate criteria; POL-002 §3.3 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-5-Discovery/P5-TL-002-AdminControlMatrix-v1.0-[DATE].docx |
| Audit Relevance | Admin matrix is cross-referenced at Gate G7 (Irreversibility Gate). Auditors verify that no undocumented admin function exists in the deployed contract. Any admin function not in the matrix is a Critical finding. |
| Notes / Exceptions | Update the admin matrix after any architecture change. Each update must be versioned and re-signed. Track B: client Product Owner must acknowledge key custody arrangements — obtain written acknowledgement and save in GW folder. |

| P5-TL-003 Complete dependency matrix (oracles, bridges, RPCs, libraries) [TRACK A + B] |  |
| --- | --- |
| Step ID | P5-TL-003 |
| Phase | Phase 5 — Discovery |
| Role | Technical Lead (TL) |
| Control Objective | Document all external protocol dependencies with failure modes and fallbacks, preventing undetected single points of failure in production. |
| Action | Complete dependency matrix (oracles, bridges, RPCs, libraries) |
| Detailed Instruction | Create the Dependency Matrix document. For every external dependency the protocol relies upon: Column headers: Dependency Name ¦ Type (oracle/bridge/RPC/library/protocol) ¦ Provider ¦ Chain ¦ Failure Mode ¦ Impact if Fails ¦ Fallback Mechanism ¦ Monitoring Approach ¦ Risk Rating (DEP-01 if SPOF) Required categories: 1. Price Oracles: Chainlink, Pyth, Band, TWAP — which feeds, what happens if feed goes stale, is there a staleness check? 2. Cross-chain bridges: if the protocol depends on a bridge for any token or message, what happens if the bridge is exploited or paused? 3. RPC / Node providers: what happens if the primary RPC is unavailable? Is there a backup? 4. External smart contract dependencies: any protocol the contracts call (e.g., Uniswap, Aave, Compound) — what if they are exploited or paused? 5. Libraries: OpenZeppelin and other library versions — are they pinned to audited versions? For any dependency rated as SPOF (no fallback, failure causes critical impact): flag as DEP-01 → requires explicit risk acceptance by Node Owner and vCISO before Phase 6 gate. The risk acceptance is recorded in the exception register (REG-506). |
| Required Input | Architecture diagrams; protocol requirements; threat model (P5-TL-001). |
| Method / Calculation / Assessment | Systematic enumeration of all import statements, external calls, and off-chain data sources in protocol design. Cross-check against threat model DEP-01 category. |
| Expected Output | Dependency Matrix document with all dependencies rated and fallback mechanisms defined. |
| Evidence Required | Dependency Matrix (signed by TL and DevOps). SPOF risk acceptance (if applicable): vCISO + Node Owner signatures. |
| Approval Required | vCISO reviews. SPOF items: Node Owner + vCISO must co-sign risk acceptance. |
| Acceptance Criteria | All external dependencies documented. Each dependency has failure mode and fallback. SPOF items are flagged and have explicit risk acceptance. No dependency is marked "no fallback" without a risk acceptance record. |
| Related Risk | DEP-01; ECON-01 (oracle manipulation) |
| Related Control | Dependency fragility assessment — STD-101 Step 5; POL-007 §4 |
| Related Policy / Standard Clause | POL-007 §4 (oracle/bridge documentation); STD-101 Step 5 Preventive Controls; POL-003 §3 DEP-01 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-5-Discovery/P5-TL-003-DependencyMatrix-v1.0-[DATE].docx |
| Audit Relevance | Dependency matrix is evidence that DEP-01 risk was systematically assessed. Auditors will verify that oracle staleness checks are in the code if the dependency matrix lists oracle price feeds. |
| Notes / Exceptions | Library versions must be pinned (not "latest"). Any library upgrade during delivery requires a change record per POL-005. |

| P5-vCISO-001 Gate G4: vCISO review and co-sign — authorize Phase 6 start [TRACK A + B] |  |
| --- | --- |
| Step ID | P5-vCISO-001 |
| Phase | Phase 5 — Discovery |
| Role | vCISO |
| Control Objective | Gate G4: Provide independent expert validation that all design-phase security requirements are met before build commences. |
| Action | Gate G4: vCISO review and co-sign — authorize Phase 6 start |
| Detailed Instruction | Review and co-sign Gate G4. Before signing, verify: 1. Threat model (P5-TL-001): all 4 categories present, signed by TL, no OPEN technical threats. 2. Admin/Control Matrix (P5-TL-002): no single EOA admin without mitigation; multisig policy defined; ADMIN-01 risk addressed. 3. Dependency Matrix (P5-TL-003): all SPOF items have explicit risk acceptances. 4. IRP draft exists (created by TL or PM, minimum contact list and incident classification). 5. PSF updated to v0.2 reflecting Discovery Phase outputs. 6. LEGAL-02 check: for DeFi/wallet/bridge protocols, confirm MSA does not imply fiduciary duty or custody. If LEGAL-02 risk is identified: flag for legal review before Gate G4 is signed. 7. For Track B: confirm client has acknowledged admin/control matrix and key custody arrangements. If any item is missing or inadequate: return to TL with specific comments. Do not sign Gate G4 with OPEN items. For T3/T4: conduct an in-person or video review session with TL before signing. |
| Required Input | Threat model; admin matrix; dependency matrix; IRP draft; PSF v0.2; RACI project instance. |
| Method / Calculation / Assessment | Document review and expert assessment. For T3/T4: structured review session with documented outputs. |
| Expected Output | Gate G4 Decision Record co-signed by TL and vCISO. Any open items from review documented with owner and resolution deadline. |
| Evidence Required | Gate G4 Decision Record (signed by TL and vCISO). Review comments from vCISO (email or memo) if any items required revision before sign-off. |
| Approval Required | vCISO (mandatory co-sign). TL (mandatory co-sign). Gate G4 requires BOTH signatures — a gate signed by TL alone is invalid. |
| Acceptance Criteria | All 7 items verified and confirmed. Gate G4 signed by both TL and vCISO. No Phase 6 development commit predates Gate G4 timestamp. |
| Related Risk | ALL Phase 5 risks — this gate validates the entire design-phase security posture |
| Related Control | Gate G4 — design-phase security gate; mandatory dual sign-off |
| Related Policy / Standard Clause | STD-101 Step 5 Gate column; POL-002 §3.5; POL-001 §5.2 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-5-Discovery/P5-vCISO-001-Gate-G4-Decision-v1.0-[DATE].docx |
| Audit Relevance | Gate G4 is the most critical design-phase evidence. Auditors will verify dual signature, verify that Phase 6 commits postdate the gate, and check that LEGAL-02 was assessed for applicable protocols. |
| Notes / Exceptions | If vCISO is unavailable for more than 3 business days, escalate to Director of Engineering for an interim gate review. vCISO must still review and confirm the gate within 5 business days of DoE interim sign-off. |

# Phase 6: Delivery (Build)

| DELIVERY | Track A + Track B — Track B adds client milestone review gate (P6-PM-002) and client communication log requirement |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 6 |
| --- | --- |
| Phase Name | Delivery (Build) |
| Phase Objective | Implement deliverables to the secure coding standard. Apply the severity-asymmetry principle: one unresolved Critical smart-contract vulnerability equals project-level risk regardless of how many minor issues are resolved. Internal audit (minimum 2 reviewers) must be complete before Phase 8. Economic simulations required for DeFi/incentive protocols. Gate G5 enforces all of these. |
| Entry Criteria | Gate G4 signed (Phase 5 complete) Threat model approved by TL + vCISO Admin/control matrix completed Security baseline active in CI/CD |
| Exit Criteria | Internal audit complete with 2-reviewer attestation All Critical/High findings resolved or formally accepted by NO + vCISO Economic simulations completed (DeFi/incentive protocols) Residual risks documented in plain English Gate G5 signed by TL (and vCISO for any open finding) |
| Key Phase Risks | SEC-CRIT-01 — Critical vulnerability undiscovered (reentrancy, auth bypass, arithmetic, oracle manipulation) ECON-02 — Gameable incentive design ("profitable but intended" exploit path) GAS-01 — Function reverts under realistic gas/block limit scenarios Hard-coded credentials committed to repository |
| Key Control Objectives | Peer code review: minimum 2 reviewers per production-bound PR; TL mandatory for smart contract code SAST gate in CI/CD: Critical/High block merge Internal audit: 2 reviewers, not authors; all Critical/High resolved before Phase 8 Economic simulation for DeFi: MEV, oracle manipulation, griefing, arbitrage scenarios |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — Track B adds client milestone review gate (P6-PM-002) and client communication log requirement |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-6-Delivery/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-06/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P6-[ROLE]-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| TL | Technical Lead | A | Leads code review; approves PRs for security-critical components; signs off internal audit; gates Gate G5 | Signs Gate G5 |
| Dev | Developer | R | Implements deliverables; responds to review findings; fixes all Critical/High before gate | N/A |
| QA | QA Engineer | R | Executes test plan covering threat model scenarios; performs internal audit (as 2nd reviewer) | Co-signs internal audit report |
| DevOps | DevOps | C | Maintains CI/CD security gates; confirms SAST active; reviews deployment configuration | N/A |
| vCISO | vCISO | C | Reviews internal audit report; must co-sign Gate G5 if any finding is formally accepted rather than resolved | Must co-sign Gate G5 if any High/Critical finding is accepted (not resolved) |
| PM | Project Manager | A | Tracks issues; manages milestone progress; schedules client milestone reviews (Track B) | N/A |
| BA | Business Analyst | C | Provides requirements traceability; confirms implemented features match security-scoped requirements | N/A |

## 3. Role-Based Checklist

| P6-TL-001 Enforce peer code review — minimum 2 reviewers per production PR [TRACK A + B] |  |
| --- | --- |
| Step ID | P6-TL-001 |
| Phase | Phase 6 — Delivery |
| Role | Technical Lead (TL) |
| Control Objective | Ensure every production-bound code change has been reviewed by a minimum of two qualified reviewers before merge, with TL as mandatory reviewer for security-critical components. |
| Action | Enforce peer code review — minimum 2 reviewers per production PR |
| Detailed Instruction | For every pull request (PR) targeting the main/production branch: 1. Reviewer requirements: - All PRs: minimum 2 approved reviews required for merge (enforce via branch protection setting). - Smart contract PRs and any security-critical code: TL must be one of the 2 reviewers. - Developer who authored the PR cannot be one of the 2 reviewers (SoD — POL-004 §2.4). 2. Review scope for smart contract PRs: - Check for reentrancy vulnerabilities (especially external calls before state updates) - Check access control: all admin functions have correct modifiers - Check arithmetic: unchecked blocks, potential overflow/underflow - Check for hard-coded addresses, keys, or secrets - Check SAST findings: CI/CD must show green (Critical/High clear) before review approval - Check that the implementation matches the threat model assumptions 3. Review documentation: - PR description must reference: (a) related ticket/issue; (b) threat model section addressed; (c) SAST scan result. - Reviewers must leave substantive comments (not just "LGTM") for any security-critical PR. - If a reviewer identifies a finding: create a GitHub/GitLab issue with severity classification before approving the PR. 4. For Critical findings identified during review: - Do not merge. Create Critical severity issue. Assign to Dev. Re-review after fix. - If the fix cannot be completed within 24 hours, notify TL and PM. Consider blocking Phase 8 gate. |
| Required Input | PR in repository; threat model (P5-TL-001) for context; SAST scan result from CI/CD. |
| Method / Calculation / Assessment | Repository PR review process enforced by branch protection. TL reviews security-critical PRs. Review comments documented in repository. |
| Expected Output | PR merged with: 2 reviewer approvals; SAST green; substantive review comments for security-critical PRs; any findings created as issues. |
| Evidence Required | Repository PR record (URL, reviewer names, approval timestamps, SAST status). Issue tracker records for any findings raised during review. (Export PR history as PDF for audit evidence package.) |
| Approval Required | TL approval required for all smart contract PRs. Any Critical finding blocks merge without TL explicit override (which itself must be documented). |
| Acceptance Criteria | Branch protection enforces 2-reviewer requirement. TL has reviewed all smart contract PRs. No Critical/High SAST finding is present in merged PRs. All findings raised during review are tracked in issue register. |
| Related Risk | SEC-CRIT-01 (critical vulnerability); hard-coded secrets |
| Related Control | Peer code review — STD-101 Step 6; POL-002 §3.1; POL-006 §2 (Phase 6 row) |
| Related Policy / Standard Clause | POL-002 §3.1 (minimum 2 reviewers); POL-004 §2.4 (SoD — author ≠ reviewer); POL-006 §2 |
| Storage Location | Repository: PR history (permanent). Google Workspace: /[Client]/[Project]/GRC/Phase-6-Delivery/evidence/PR-review-log-[DATE].pdf |
| Audit Relevance | Auditors will pull PR history and verify reviewer names, approval counts, and SAST status. Any merged PR with fewer than 2 approvals or with a Critical SAST finding unresolved is a control failure. |
| Notes / Exceptions | Track B: client engineers may be given read access to the repository but cannot be counted as one of the 2 required reviewers unless they have been vetted and included in the RACI. |

| P6-QA-001 Conduct internal audit (2 independent reviewers, not code authors) [TRACK A + B] |  |
| --- | --- |
| Step ID | P6-QA-001 |
| Phase | Phase 6 — Delivery |
| Role | QA Engineer (QA) |
| Control Objective | Conduct a comprehensive internal audit by reviewers who are not the code authors, ensuring independent identification of Critical and High vulnerabilities before the testnet gate. |
| Action | Conduct internal audit (2 independent reviewers, not code authors) |
| Detailed Instruction | Internal audit must be completed before Gate G5 and before testnet deployment (Phase 8). Process: 1. Audit team composition: - Minimum 2 reviewers. - Neither reviewer may have authored the code being audited. - TL must be one reviewer for smart contract audits. - QA Engineer is the second reviewer (or a second qualified developer who did not author). - For T3/T4: consider using a developer from a different Node as the second reviewer. 2. Audit scope — mandatory for all Web3 protocols: - All smart contract code in scope for production deployment. - Access control logic (roles, modifiers). - All external calls and state mutation ordering. - Gas consumption under worst-case scenarios. - Upgrade mechanism (if proxy pattern). - Initialization logic. - All functions listed in the admin/control matrix. 3. Audit methodology: - Manual code review line-by-line for security-critical contracts. - Cross-reference against threat model (P5-TL-001) — every threat must have a corresponding code-level check. - Run Slither (or equivalent) in full mode and review all findings. - Run Echidna (or equivalent) fuzz testing on critical invariants. 4. Findings documentation: - Each finding: ID, title, severity (Critical/High/Medium/Low/Info), description, proof-of-concept (where possible), recommendation. - All Critical and High findings must be resolved before Phase 8. Resolution confirmed by re-audit of the fix. 5. Audit report: - Summary: lines of code reviewed, reviewer names, audit scope, audit date. - Finding table with disposition (Resolved / Accepted / Out of Scope). - Both reviewers sign the report. |
| Required Input | Complete smart contract codebase (frozen for audit — no commits during audit); threat model (P5-TL-001); admin/control matrix (P5-TL-002). |
| Method / Calculation / Assessment | Manual review + automated tooling (Slither, Echidna). Each reviewer completes independently before consolidation. |
| Expected Output | Internal audit report: signed by both reviewers; finding table with severity, status, and resolution notes. |
| Evidence Required | Internal audit report (signed by TL + QA/2nd reviewer). Finding resolution records (PRs fixing each Critical/High finding, with TL review approval). SAST and fuzz tool output attached as appendix. |
| Approval Required | TL must sign audit report. QA/2nd reviewer must sign. For any Critical/High finding formally ACCEPTED (not resolved): Node Owner + vCISO must co-sign the acceptance. |
| Acceptance Criteria | All Critical and High findings RESOLVED (re-audited) or ACCEPTED with Node Owner + vCISO sign-off. Audit report signed by 2 reviewers who are not code authors. Finding resolution is traceable to PR records. |
| Related Risk | SEC-CRIT-01 (critical vulnerability undiscovered) |
| Related Control | Internal audit — STD-101 Step 6; POL-006 §2 (Phase 6/internal audit row) |
| Related Policy / Standard Clause | POL-006 §2 (internal audit: 2 reviewers, not authors); POL-002 §3.5; STD-101 Step 6 Gate criteria |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-6-Delivery/P6-QA-001-InternalAudit-v1.0-[DATE].docx Tool outputs: /[Client]/[Project]/GRC/Phase-6-Delivery/evidence/audit-tool-output/ |
| Audit Relevance | Internal audit report is the primary Phase 6 audit evidence. Auditors will verify: (1) 2 reviewer names (not code authors); (2) all Critical/High findings are resolved or have formal acceptance; (3) audit predates Phase 8 gate. |
| Notes / Exceptions | If the protocol is DeFi or incentive-bearing: economic simulation results (P6-TL-002) must be reviewed by the audit team and any economic exploit findings included in the audit report. |

| P6-TL-002 Conduct economic simulations for DeFi and incentive-bearing protocols [TRACK A + B] |  |
| --- | --- |
| Step ID | P6-TL-002 |
| Phase | Phase 6 — Delivery |
| Role | Technical Lead (TL) |
| Control Objective | Identify gameable incentive mechanisms and economic exploit paths before deployment, as these are not detectable by standard SAST tools and represent a class of Web3-specific risk. |
| Action | Conduct economic simulations for DeFi and incentive-bearing protocols |
| Detailed Instruction | Required for all protocols that include: token incentives, liquidity mining, yield, borrowing/lending, AMM mechanics, bridge fees, staking rewards, or any value extraction mechanism. Simulate the following attack scenarios (minimum): 1. MEV / Sandwich Attack: - Can an attacker profit by front-running and back-running a user transaction? - Is there slippage protection? What is the maximum loss per transaction? 2. Oracle Manipulation: - Simulate a large capital position acquiring spot price control (flash loan or whale). - Can the attacker move the oracle price enough to: trigger false liquidations, drain reserves, or extract protocol-held tokens? - Is TWAP used? What is the minimum TWAP window? Can it be manipulated within the window? 3. Griefing: - Can an attacker make the protocol unusable for others at low attacker cost? - Example: filling all available slots, triggering gas limit failures, spamming state updates. 4. Incentive Gaming ("profitable but intended"): - Is there an action sequence that extracts value the protocol did not intend to distribute? - Example: staking just before reward snapshot and unstaking immediately after. - These are not "bugs" but are design flaws — they must be documented and either accepted or mitigated. 5. Token Economic Simulation: - Model token supply dynamics under maximum incentive extraction scenarios. - Identify if protocol reserves can be drained faster than expected under adversarial behavior. Document each simulation: scenario, tool/method used, result, conclusion (Exploitable/Mitigated/Accepted), and recommended fix if Exploitable. |
| Required Input | Threat model (P5-TL-001, Category 2); protocol tokenomics documentation; smart contract code. |
| Method / Calculation / Assessment | Agent-based simulation (Foundry fuzzing, custom scripts, or specialist tools such as Gauntlet/Certora where budget allows). Results documented in simulation report. |
| Expected Output | Economic simulation report: all 5 scenario categories covered, results documented, ECON-02 risks rated. |
| Evidence Required | Economic simulation report (signed by TL). Tool outputs (scripts, logs) saved in evidence folder. Any ECON-02 OPEN items tracked in issue register. |
| Approval Required | vCISO reviews simulation report. Any ECON-02 exploit path rated Critical requires Node Owner + vCISO formal acceptance before proceeding. |
| Acceptance Criteria | All 5 scenario categories simulated. Each scenario has a result and conclusion. No Exploitable scenario proceeds to Phase 8 without formal risk acceptance. Report signed by TL. |
| Related Risk | ECON-01; ECON-02 |
| Related Control | Economic simulations — STD-101 Step 6; POL-006 §2 (economic simulation row) |
| Related Policy / Standard Clause | POL-006 §2 (economic simulation requirement for DeFi); POL-003 §3 ECON-01/ECON-02 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-6-Delivery/P6-TL-002-EconomicSimulation-v1.0-[DATE].docx Scripts: /[Client]/[Project]/GRC/Phase-6-Delivery/evidence/simulation-scripts/ |
| Audit Relevance | Economic simulations are a Web3-specific control with no direct NIST equivalent. Auditors from Web3-specialist firms will specifically look for simulation evidence for DeFi protocols. |
| Notes / Exceptions | If the team lacks in-house capability for economic simulations, engage an external economic security specialist. This cost should have been estimated in P2-TL-001. If not budgeted, escalate to Node Owner. |

| P6-TL-003 Gate G5: Internal audit completion and Phase 6 → Phase 8 authorization [TRACK A + B] |  |
| --- | --- |
| Step ID | P6-TL-003 |
| Phase | Phase 6 — Delivery |
| Role | Technical Lead (TL) |
| Control Objective | Gate G5: Confirm that all build-phase security controls are complete and that Phase 8 (Testnet) can commence with no unresolved Critical/High issues. |
| Action | Gate G5: Internal audit completion and Phase 6 → Phase 8 authorization |
| Detailed Instruction | Review and sign Gate G5. Before signing, confirm: 1. Internal audit report (P6-QA-001) is complete, signed by 2 reviewers, all Critical/High findings RESOLVED or ACCEPTED. 2. Economic simulations (P6-TL-002) complete and no OPEN ECON-02 exploits without formal acceptance. 3. SAST is currently green (no Critical/High) in CI/CD — run a fresh scan and attach the output. 4. No hard-coded secrets, keys, or credentials in any merged branch (verify secret scanning log). 5. Residual risk summary document exists: a plain-English list of known limitations, design tradeoffs, and accepted risks. This document will be used in the client-facing security posture document at Phase 10. 6. For Track B: client milestone review conducted (P6-PM-002) and client has no blocking issues. 7. PSF updated to v0.3 reflecting internal audit outcomes. For any Critical/High finding that is ACCEPTED (not resolved): Node Owner and vCISO must co-sign Gate G5 alongside TL. |
| Required Input | Internal audit report; economic simulation report; SAST scan output (fresh); secret scanning log; residual risk summary; PSF v0.3. |
| Method / Calculation / Assessment | Document review and sign-off. Fresh SAST scan must be no older than 24 hours at time of gate signing. |
| Expected Output | Gate G5 Decision Record: signed by TL. If any accepted findings: also signed by NO and vCISO. |
| Evidence Required | Gate G5 Decision Record (signed). Fresh SAST scan output attached. Internal audit report (signed) referenced. Residual risk summary in project folder. |
| Approval Required | TL (mandatory). If any accepted Critical/High finding: Node Owner + vCISO co-sign required. |
| Acceptance Criteria | Gate G5 signed. SAST green (Critical/High clear). Internal audit signed by 2 reviewers. No unaddressed Critical/High findings. Residual risk summary exists. |
| Related Risk | SEC-CRIT-01; ECON-02; GAS-01 |
| Related Control | Gate G5 — build-phase security gate; severity-asymmetry enforcement |
| Related Policy / Standard Clause | STD-101 Step 6 Gate column; POL-006 §2; POL-001 §5.2 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-6-Delivery/P6-TL-003-Gate-G5-Decision-v1.0-[DATE].docx |
| Audit Relevance | Gate G5 is the build-phase exit gate. Auditors will verify that no Phase 8 testnet deployment occurred before Gate G5 was signed. |
| Notes / Exceptions | If Phase 7 (Demo) occurs before Phase 8, Gate G5 may be signed after the demo. However, any security-critical code must not be deployed to any environment (including demo environments) before Gate G5 standards are met for that code. |

| P6-PM-002 [TRACK B ONLY] Conduct client milestone review and communication log [TRACK B] |  |
| --- | --- |
| Step ID | P6-PM-002 |
| Phase | Phase 6 — Delivery |
| Role | Project Manager (PM) |
| Control Objective | For Track B: ensure client is kept informed of delivery progress, security findings, and design decisions that affect their project, preventing discovery of issues at late gates. |
| Action | [TRACK B ONLY] Conduct client milestone review and communication log |
| Detailed Instruction | For Track B only. At each major milestone during Phase 6 (minimum once per 2-week sprint): 1. Prepare a milestone update for the client covering: features delivered; open issues (severity-classified — do not share Critical finding details publicly; share as "critical security issue — under remediation"); timeline status; any changes to security scope. 2. For DeFi/incentive protocols: share economic simulation progress with client technical contact (not full report if it contains sensitive attack details — provide a summary). 3. Record client feedback in the communication log. 4. If client raises a change request that affects security scope (e.g., removing a feature that provides a security control): escalate to TL and vCISO before acknowledging the request. 5. Maintain a communication log: date, attendees, decisions, action items. |
| Required Input | Sprint/milestone progress from PM tool; internal audit status; economic simulation status. |
| Method / Calculation / Assessment | Regular meeting or written update. Communication log maintained in GW project folder. |
| Expected Output | Communication log with at least one entry per 2-week period. Client change requests documented and routed correctly. |
| Evidence Required | Communication log (versioned in GW). Meeting minutes or email threads with client (dated). Change request records (if any). |
| Approval Required | PM owns this step. TL and vCISO must be notified of any client request that touches security scope. |
| Acceptance Criteria | Communication log exists with entries for each sprint. No change request affecting security scope was implemented without TL + vCISO review. Log is version-controlled. |
| Related Risk | Scope creep; OPS-01 (responsibility shift) |
| Related Control | Client communication log — Track B governance artifact |
| Related Policy / Standard Clause | POL-001 §5.1 (Track B co-delivery model); RACI-001 §4 (customer communication) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-6-Delivery/P6-PM-002-TrackB-CommLog-v[N]-[DATE].docx |
| Audit Relevance | Track B auditors will verify that client was informed of security status throughout delivery, not only at gates. |
| Notes / Exceptions | TRACK B ONLY. Do not share full internal audit reports or full economic simulation outputs with client without Node Owner and vCISO approval. |

# Phase 7: Demo

| DELIVERY | Track A + Track B — Demo audience differs: Track A is internal/stakeholder; Track B requires client attendance and sign-off |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 7 |
| --- | --- |
| Phase Name | Demo |
| Phase Objective | Demonstrate deliverables to client and internal stakeholders. Capture all issues raised during demonstration. This is a milestone gate within the delivery phase — any Critical security issue identified during demo must trigger re-entry to Phase 6 before Phase 8 proceeds. |
| Entry Criteria | Gate G5 signed (Phase 6 complete) Internal audit complete with no unresolved Critical/High findings Demo environment prepared from approved testnet build |
| Exit Criteria | Demo conducted with meeting minutes recorded All issues captured in issue register with severity classification Decision recorded: proceed to Phase 8 / return to Phase 6 for rework No Critical security issue found during demo is open |
| Key Phase Risks | Critical issue identified at demo that was missed in internal audit Client acceptance failure exposing scope ambiguity Issues requiring re-entry to Phase 6 (re-audit cycle) |
| Key Control Objectives | Demo environment must be built from the same commit as the internal audit All issues raised during demo classified by severity within 24 hours TL assesses whether any issue requires a new Phase 6 security cycle before Phase 8 |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — Demo audience differs: Track A is internal/stakeholder; Track B requires client attendance and sign-off |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-7-Demo/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-07/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P7-[ROLE]-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| PM | Project Manager | A | Schedules demo; records meeting minutes; issues register update | Signs Gate G5-B decision |
| TL | Technical Lead | R | Delivers technical demo; assesses security implications of issues raised | Assesses whether any issue requires Phase 6 re-entry |
| Dev | Developer | R | Supports demo delivery; addresses questions on implementation | N/A |
| AM | Account Manager | I | Attends demo; manages client expectations; escalates client concerns | N/A |
| NO | Node Owner | I | Optionally attends; informed of issues requiring re-entry to Phase 6 | Approves re-entry to Phase 6 if required |
| CUST | Customer/Product Owner | I | Track B: attends demo; provides formal feedback; signs meeting minutes | Track B: signs Gate G5-B meeting minutes as acknowledgement |

## 3. Role-Based Checklist

| P7-PM-001 Prepare demo environment and confirm build consistency [TRACK A + B] |  |
| --- | --- |
| Step ID | P7-PM-001 |
| Phase | Phase 7 — Demo |
| Role | Project Manager (PM) |
| Control Objective | Ensure the demo is conducted from an auditably consistent build, preventing demonstration of code that has not passed the Phase 6 security controls. |
| Action | Prepare demo environment and confirm build consistency |
| Detailed Instruction | Before scheduling the demo: 1. Confirm the demo environment is built from the same commit hash as the internal audit (P6-QA-001). Document the commit hash in the demo setup record. 2. Confirm SAST scan result was green on this commit. 3. Set up the demo environment (can be a local testnet, hosted testnet, or staging environment — must NOT be mainnet or contain real funds > $1K). 4. Prepare demo script: list of features to be demonstrated, expected behavior, known limitations to disclose. 5. Brief TL on any client questions or concerns identified in the communication log (Track B: P6-PM-002). 6. Confirm demo attendees: for Track B, confirm client Product Owner is attending. Record attendee confirmation emails. |
| Required Input | Gate G5 Decision Record (P6-TL-003); internal audit commit reference; communication log (Track B). |
| Method / Calculation / Assessment | Environment setup and consistency check. Commit hash verified against audit record. |
| Expected Output | Demo Setup Record: commit hash, environment URL, attendee list, demo script. |
| Evidence Required | Demo Setup Record (PM signed). Commit hash reference matches internal audit record. Attendee confirmation records. |
| Approval Required | TL confirms commit hash is correct. PM sign-off on demo readiness. |
| Acceptance Criteria | Demo environment commit hash matches internal audit commit. Environment does not contain real funds > $1K. Demo script prepared. Attendees confirmed. |
| Related Risk | Demo from incorrect build (un-audited code); client sees different code than was audited |
| Related Control | Build consistency check — ensures demo and audit are of the same code |
| Related Policy / Standard Clause | POL-001 §5.2 (gate criteria); POL-008 §2 (demo minutes as evidence) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-7-Demo/P7-PM-001-DemoSetup-v1.0-[DATE].docx |
| Audit Relevance | Auditors will verify that demo commit hash matches audit commit hash. Mismatched hashes indicate the demo was conducted on un-audited code. |
| Notes / Exceptions | If the demo environment requires a different configuration than the audit environment, document ALL differences explicitly. Any difference that introduces a new code path requires TL review. |

| P7-PM-002 Record demo meeting minutes and classify all issues raised [TRACK A + B] |  |
| --- | --- |
| Step ID | P7-PM-002 |
| Phase | Phase 7 — Demo |
| Role | Project Manager (PM) |
| Control Objective | Capture all issues raised during the demo with severity classification, ensuring no issue is lost between demo and Phase 8 gate. |
| Action | Record demo meeting minutes and classify all issues raised |
| Detailed Instruction | During or immediately after the demo (within 24 hours): 1. Record meeting minutes: date, attendees (full names and roles), demo scope, issues raised. 2. For each issue raised: create an entry in the project issue register with: - Issue description - Raised by (name and role) - Severity classification (TL assigns within 24 hours of demo): Critical / High / Medium / Low / Enhancement - Assigned to (Dev) - Target resolution: before Phase 8 gate (Critical/High) or before Phase 9 gate (Medium) or post-deployment (Low/Enhancement) 3. If any issue is classified Critical by TL: immediately flag to PM and Node Owner. Gate G5-B outcome is "Return to Phase 6" for this issue. 4. Record the overall demo outcome decision: Proceed to Phase 8 / Return to Phase 6 for rework on specific issues. 5. For Track B: obtain client attendee signature on meeting minutes (or email acknowledgement within 24 hours). |
| Required Input | Demo notes; issue identification during demo; TL severity assessment. |
| Method / Calculation / Assessment | Meeting minutes in standard template. Issue register update. TL assesses severity within 24 hours. |
| Expected Output | Demo Meeting Minutes (signed by PM). Issue register updated with all demo-identified issues. Gate G5-B Decision Record. |
| Evidence Required | Demo Meeting Minutes (PM + TL signed; Track B: client signed or email acknowledgement). Issue register entries with severity and assignment. Gate G5-B Decision Record. |
| Approval Required | TL classifies severity. PM signs minutes. Track B: client acknowledgement of meeting record. |
| Acceptance Criteria | Minutes exist with all attendees named. All issues logged in issue register with severity. Critical issues trigger re-entry decision. Gate G5-B decision is recorded within 24 hours of demo. |
| Related Risk | Issue lost between demo and Phase 8; Critical issue proceeds to testnet without resolution |
| Related Control | Demo issue capture — ensures no issue is lost; severity-asymmetry applied at demo stage |
| Related Policy / Standard Clause | POL-001 §5.2 (Gate G5-B); POL-008 §2 (demo minutes as evidence); POL-003 §3 (issue severity) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-7-Demo/P7-PM-002-DemoMinutes-v1.0-[DATE].docx P7-PM-002-Gate-G5B-Decision-v1.0-[DATE].docx |
| Audit Relevance | Demo minutes are audit evidence that Phase 8 was preceded by client/stakeholder review. Issue register entries from demo are traced to Phase 8 gate resolution records. |
| Notes / Exceptions | Track B: if client identifies a Critical security issue during demo that was missed in internal audit, this is a Phase 6 gate failure — notify vCISO immediately. |

# Phase 8: Testnet Deployment

| DELIVERY | Track A + Track B — Track B requires client to co-sign testnet runbook results (P8-TL-004) |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 8 |
| --- | --- |
| Phase Name | Testnet Deployment |
| Phase Objective | Execute full deployment on testnet under production-equivalent conditions using the exact same runbook that will be used at Phase 9 (mainnet). Test every admin function. Validate monitoring. This is the final opportunity to identify deployment-specific failures before the irreversible mainnet event. |
| Entry Criteria | Gate G5 signed (Phase 6 complete) Gate G5-B signed (Phase 7 complete) All Critical/High audit findings resolved or formally accepted Economic simulations complete (DeFi protocols) |
| Exit Criteria | Full deployment runbook executed on testnet All admin functions tested (pause, upgrade, drain, fee change) with two-person rule Monitoring and alerting live on testnet and validated External audit engagement letter signed (if required: TVL > $1M / DeFi/Bridge / Score ≥ 3.0) Fuzz/property tests passing against testnet deployment Gate G6 signed by TL and DevOps (and vCISO for external audit check) |
| Key Phase Risks | DEPLOY-FATAL-01 — Wrong owner/admin address set during deployment PAUSE-FATAL-01 — Pause function untested and unusable in emergency ADMIN-01 — Multisig not tested in real deployment context GAS-01 — Deployment fails under realistic gas conditions |
| Key Control Objectives | Full deployment runbook executed on testnet before mainnet Two-person rule enforced at testnet deployment All admin functions dry-run on testnet Monitoring validated against testnet before Phase 9 External audit initiated where required (P3 ≥ 3 or DeFi/bridge) |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — Track B requires client to co-sign testnet runbook results (P8-TL-004) |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-8-Testnet/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-08/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P8-[ROLE]-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| TL | Technical Lead | A | Owns deployment runbook; signs off testnet results; verifies all admin functions | Signs Gate G6 (co-sign with DevOps) |
| DevOps | DevOps Engineer | R | Executes deployment; configures monitoring; validates alerts on testnet | Co-signs Gate G6 |
| Dev | Developer | R | Supports deployment execution; fixes any deployment-specific issues found on testnet | N/A |
| QA | QA Engineer | R | Executes fuzz/property tests against testnet deployment; validates test results | Signs fuzz test report |
| vCISO | vCISO | C | Conducts Irreversibility Pre-Check (preview of Phase 9 gate); confirms external audit status | Must confirm external audit engagement is in place before Gate G6 if required |
| NO | Node Owner | I | Informed of testnet results; approves external audit engagement and cost | Approves external audit engagement letter |
| PM | Project Manager | I | Tracks testnet progress; schedules Gate G6 review; Track B: coordinates client review | N/A |

## 3. Role-Based Checklist

| P8-TL-001 Execute full deployment runbook on testnet (two-person rule) [TRACK A + B] |  |
| --- | --- |
| Step ID | P8-TL-001 |
| Phase | Phase 8 — Testnet Deployment |
| Role | Technical Lead (TL) |
| Control Objective | Execute the deployment runbook on testnet exactly as it will be run on mainnet, ensuring the runbook is validated and deployment-specific failures are identified before the irreversible mainnet deployment. |
| Action | Execute full deployment runbook on testnet (two-person rule) |
| Detailed Instruction | Deploy to testnet using the production deployment runbook. The runbook must be pre-written and version-controlled before testnet execution begins. Runbook must include: 1. Pre-deployment checks: [ ] Commit hash to deploy: [specify] [ ] Deployer wallet address: [specify] [ ] Admin/multisig addresses: [specify each signer] [ ] RPC endpoint: [specify — primary and backup] [ ] Gas price strategy: [specify] [ ] Deployment script path: [specify] 2. Deployment steps (numbered, sequential): [ ] Step 1: Deploy contract [name] — expected address: [TBD pre-deploy] [ ] Step 2: Verify contract on explorer [ ] Step 3: Initialize [specify function] with params [specify] [ ] Step 4: Transfer ownership to multisig [address] [ ] Step 5: Verify ownership on-chain: call owner() — expected: [multisig address] [ ] [Continue for all contracts] 3. Post-deployment verification: [ ] Verify all on-chain state matches expected configuration [ ] Verify multisig is active (test send + sign) [ ] Verify pause function works (pause → verify state → unpause) [ ] Verify timelock is active (if applicable) Two-person rule: Deployer (Dev or DevOps) and Approver (TL) must be different individuals. Approver witnesses and co-signs each critical step in the runbook. Record actual addresses, transaction hashes, and block numbers for each deployment step. |
| Required Input | Production deployment runbook (pre-written); admin/control matrix (P5-TL-002); testnet RPC access; deployer wallet. |
| Method / Calculation / Assessment | Sequential execution of runbook steps. Each step checked off with actual result recorded. Two-person attestation for each critical step. |
| Expected Output | Completed testnet runbook with actual results filled in: all addresses, transaction hashes, block numbers, step results. |
| Evidence Required | Completed testnet runbook (signed by Deployer + Approver/TL). Transaction hashes (linked to testnet explorer). Post-deployment state verification screenshot. |
| Approval Required | TL (Approver role in two-person rule). DevOps (Deployer role). Both must sign the completed runbook. |
| Acceptance Criteria | All runbook steps completed and checked off. Actual results recorded for each step. Ownership verified on-chain. Two-person attestation signed. Transaction hashes are real testnet hashes (verifiable on explorer). |
| Related Risk | DEPLOY-FATAL-01; PAUSE-FATAL-01 |
| Related Control | Testnet deployment runbook — STD-101 Step 8; mandatory before Phase 9 |
| Related Policy / Standard Clause | POL-005 §3.2 (on-chain change mini-cycle); STD-101 Step 8 Preventive Controls; POL-004 §2.5 (two-person rule) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-8-Testnet/P8-TL-001-TestnetRunbook-Completed-v1.0-[DATE].docx Transaction hashes: /[Client]/[Project]/GRC/Phase-8-Testnet/evidence/testnet-txhashes.txt |
| Audit Relevance | Testnet runbook is the primary Phase 8 deployment evidence. Auditors verify: (1) transaction hashes are real testnet transactions; (2) ownership verification is documented; (3) two-person attestation is present. A runbook without real transaction hashes fails audit. |
| Notes / Exceptions | If any step in the testnet runbook fails: stop, document the failure, fix, and re-run from the failed step. Do not proceed to Phase 9 until the full runbook has been completed without failures. |

| P8-DevOps-001 Configure and validate monitoring and alerting against testnet [TRACK A + B] |  |
| --- | --- |
| Step ID | P8-DevOps-001 |
| Phase | Phase 8 — Testnet Deployment |
| Role | DevOps Engineer (DevOps) |
| Control Objective | Validate that on-chain monitoring and alerting is operational before mainnet deployment, ensuring incident detection capability is live from the moment of production deployment. |
| Action | Configure and validate monitoring and alerting against testnet |
| Detailed Instruction | Set up and validate on-chain monitoring against the testnet deployment: 1. Configure monitoring for the following event types: - All admin function calls (pause, upgrade, ownership transfer, drain) - Large value transfers (threshold: > 10% of TVL or > $100K equivalent) - Failed transactions on critical functions (gas issues, reverts) - Oracle price deviation > X% from baseline (configure threshold based on protocol design) - Governance proposals created and executed - Any event defined in the admin/control matrix as a monitoring trigger 2. Tools (acceptable options): - Tenderly (recommended for EVM): set up alert rules for above events - Forta Network: deploy agent for custom protocol monitoring - OpenZeppelin Defender: sentinel alerts - Custom webhook: if custom solution, document architecture and test thoroughly 3. Validation test: - Trigger each alert type deliberately on testnet and confirm alert fires within 60 seconds. - Confirm alert is received by: DevOps on-call AND vCISO email/Slack. - Document each test: event triggered, timestamp, alert received timestamp, recipient confirmed. 4. Document monitoring configuration: - Tool name and version - Alert rules configured (list each) - Alert recipients - Escalation path if primary recipient is unavailable - On-call schedule for DevOps |
| Required Input | Testnet deployment addresses (P8-TL-001); admin/control matrix (P5-TL-002); monitoring tool access. |
| Method / Calculation / Assessment | Monitoring configuration and deliberate alert trigger testing. Results documented. |
| Expected Output | Monitoring Configuration Document + Alert Validation Log: each alert type tested, result recorded, recipients confirmed. |
| Evidence Required | Monitoring Configuration Document (signed by DevOps). Alert Validation Log with timestamps (each test: event triggered, alert received, recipient confirmed). Screenshot of monitoring dashboard showing testnet deployment addresses. |
| Approval Required | vCISO must confirm receipt of test alerts (email or Slack confirmation with timestamp). TL reviews monitoring coverage against admin/control matrix. |
| Acceptance Criteria | All admin function call types are monitored. Large value transfers are monitored. Each alert type validated with real testnet trigger. vCISO confirmed as recipient. Alert latency < 60 seconds for all critical alerts. |
| Related Risk | MON-01 (no on-chain monitoring); CHAIN-FATAL-01 (exploit not detected) |
| Related Control | On-chain monitoring activation — STD-101 Step 8; POL-010 §2 (continuous monitoring) |
| Related Policy / Standard Clause | POL-010 §2 (on-chain monitoring, continuous); STD-101 Step 8 Preventive Controls; KRI-01/POL-010 §3 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-8-Testnet/P8-DevOps-001-MonitoringConfig-v1.0-[DATE].docx Alert validation log: /[Client]/[Project]/GRC/Phase-8-Testnet/evidence/alert-validation-log.xlsx |
| Audit Relevance | Monitoring is a mandatory Gate G6 criterion. Auditors verify that monitoring was validated on testnet, not assumed to work on mainnet. |
| Notes / Exceptions | If monitoring tool is a paid subscription: confirm subscription is active and will cover the production deployment. Do not allow monitoring to lapse due to billing issues. |

| P8-TL-002 Gate G6: Testnet completion review — authorize Phase 9 start [TRACK A + B] |  |
| --- | --- |
| Step ID | P8-TL-002 |
| Phase | Phase 8 — Testnet Deployment |
| Role | Technical Lead (TL) |
| Control Objective | Gate G6: Confirm all testnet gate criteria are satisfied before authorizing the irreversible mainnet deployment at Phase 9. |
| Action | Gate G6: Testnet completion review — authorize Phase 9 start |
| Detailed Instruction | Review and sign Gate G6. Before signing, confirm each item: [ ] 1. Testnet runbook completed without failures, signed by deployer + TL (P8-TL-001) [ ] 2. All admin functions tested on testnet (pause confirmed working, ownership verified) [ ] 3. Two-person rule applied and attested in runbook [ ] 4. Monitoring validated — vCISO confirmed as alert recipient (P8-DevOps-001) [ ] 5. Fuzz/property tests passing against testnet deployment (P8-QA-001 — if completed; if outstanding, must be completed before Phase 9 gate) [ ] 6. External audit: if required (TVL > $1M / DeFi/Bridge / Score ≥ 3.0): engagement letter signed by audit firm and Node Owner, and audit is scheduled to complete before Phase 9. [ ] 7. All Critical/High findings from internal audit are RESOLVED (re-verify against testnet — no new issues introduced in post-audit fixes). [ ] 8. PSF updated to v0.4 reflecting testnet results. [ ] 9. Track B: client has co-signed testnet runbook results (P8-TL-004). For items not yet complete at time of Gate G6 review: create a Pre-Phase-9 checklist with deadlines. Gate G6 is a conditional approval only. Phase 9 gate (G7) will enforce completion of all items. |
| Required Input | Testnet runbook (completed); monitoring validation log; external audit engagement letter (if applicable); fuzz test report; PSF v0.4. |
| Method / Calculation / Assessment | Review and conditional or full sign-off. |
| Expected Output | Gate G6 Decision Record: signed by TL and DevOps. Any outstanding items listed in Pre-Phase-9 checklist with deadlines. |
| Evidence Required | Gate G6 Decision Record (TL + DevOps signed). External audit engagement letter (if applicable). Fuzz test report. |
| Approval Required | TL and DevOps co-sign. vCISO confirms external audit status (if applicable). NO approves external audit cost. |
| Acceptance Criteria | Gate G6 signed by TL and DevOps. All testnet gate criteria confirmed or documented with deadline. External audit confirmed (if required). No Phase 9 deployment scheduled before all outstanding items are closed. |
| Related Risk | DEPLOY-FATAL-01; PAUSE-FATAL-01; MON-01; external audit not in place |
| Related Control | Gate G6 — testnet exit gate; prerequisite for irreversibility gate |
| Related Policy / Standard Clause | STD-101 Step 8 Gate column; POL-006 §2 (external audit conditions); POL-001 §5.2 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-8-Testnet/P8-TL-002-Gate-G6-Decision-v1.0-[DATE].docx |
| Audit Relevance | Gate G6 is the Phase 8 exit gate. Auditors will verify that all Phase 9 mainnet deployment timestamps are later than Gate G6 sign-off. |
| Notes / Exceptions | If external audit is required but not yet complete at Gate G6: Phase 9 is blocked until the audit report is received and all Critical/High findings resolved. No exception is permitted without vCISO written approval. |

| P8-TL-004 [TRACK B ONLY] Client review and acknowledgement of testnet results [TRACK B] |  |
| --- | --- |
| Step ID | P8-TL-004 |
| Phase | Phase 8 — Testnet Deployment |
| Role | Technical Lead (TL) |
| Control Objective | For Track B: obtain client acknowledgement of testnet results, ensuring client accepts the security posture before mainnet deployment proceeds. |
| Action | [TRACK B ONLY] Client review and acknowledgement of testnet results |
| Detailed Instruction | For Track B only. Prepare a testnet results summary for the client covering: 1. What was deployed on testnet (contract names, addresses). 2. What was tested (admin functions, monitoring, fuzz tests). 3. Summary of audit status (internal audit complete; external audit status). 4. Any known issues or limitations discovered during testnet that will be addressed before mainnet or accepted as residual risk. 5. Confirmation that monitoring is live and who receives alerts. Share the summary with the client Product Owner and request written acknowledgement. The acknowledgement must confirm: (a) client has reviewed the testnet results; (b) client accepts the residual risk summary; (c) client confirms readiness for mainnet deployment. If the client raises new concerns: route to TL for assessment. Do not proceed to Phase 9 if client has unresolved Critical concerns. |
| Required Input | Testnet runbook results; internal audit report (or summary); external audit status; monitoring validation record. |
| Method / Calculation / Assessment | Written summary prepared by TL. Client review and written acknowledgement. |
| Expected Output | Testnet Results Summary (Track B version). Client written acknowledgement (email or signed document). |
| Evidence Required | Testnet Results Summary (TL signed). Client acknowledgement email (exported PDF, dated) or signed document. |
| Approval Required | TL owns content. Node Owner reviews before sharing. Client must acknowledge before Phase 9 gate. |
| Acceptance Criteria | Testnet Results Summary covers all 5 items. Client written acknowledgement received from named client representative. Any client concern is documented and resolved before Phase 9 gate. |
| Related Risk | Client disputes post-deployment that they were not informed of known risks; liability risk |
| Related Control | Client testnet sign-off — Track B accountability control |
| Related Policy / Standard Clause | POL-001 §5.1 (Track B); STD-101 Step 8; POL-008 §2 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-8-Testnet/P8-TL-004-TrackB-TestnetSignoff-v1.0-[DATE].pdf |
| Audit Relevance | Track B client acknowledgement of testnet results is evidence that client was informed of the security posture before consenting to mainnet deployment. |
| Notes / Exceptions | TRACK B ONLY. For protocols with TVL > $1M: client acknowledgement at this stage should also confirm they understand that the external audit report must be received and reviewed before mainnet. Document this explicitly. |

# Phase 9: Production Deployment

| IRREVERSIBILITY | Track A + Track B — highest-risk event in the entire lifecycle; Track B requires client formal acceptance of go-live (P9-AM-001) |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 9 |
| --- | --- |
| Phase Name | Production Deployment |
| Phase Objective | Execute irreversible mainnet deployment. Every gate criterion must be satisfied. No code-level rollback is possible after mainnet deployment. The Irreversibility Gate Record (signed by Node Owner, Technical Lead, and vCISO) is the mandatory authorization artifact. The two-person rule applies to the deployment execution itself. |
| Entry Criteria | Gate G6 signed (Phase 8 complete) Testnet runbook validated All Critical/High audit findings resolved External audit report received with no unresolved Critical/High (if required) Monitoring validated on testnet Track B: client testnet acknowledgement received |
| Exit Criteria | All 7 Hard Stop conditions verified CLEAR On-chain ownership verified post-deployment Production monitoring live and validated Irreversibility Gate Record signed by NO + TL + vCISO Deployment executed with two-person rule Post-deployment state verified on-chain |
| Key Phase Risks | DEPLOY-FATAL-01 — Wrong owner/admin address set (irrecoverable) PAUSE-FATAL-01 — Pause function unusable in production MON-01 — Monitoring not live at go-live (exploit undetected) CHAIN-FATAL-01 — No recovery path for critical exploit HS-06 — Phase 9 proceeds without Irreversibility Gate clearance HS-07 — Custody/key ownership ambiguous at time of deployment |
| Key Control Objectives | 7 Hard Stop verification mandatory (HS-01 through HS-07) Two-person rule: deployer and approver are different individuals On-chain ownership verification before any public announcement Production monitoring live before go-live External audit signed off (if required) Irreversibility Gate Record signed by all three mandatory signatories |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — highest-risk event in the entire lifecycle; Track B requires client formal acceptance of go-live (P9-AM-001) |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-9-ProductionDeployment/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-09/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P9-[ROLE]-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| NO | Node Owner | A | Signs Irreversibility Gate Record; accepts business risk; informs CEO for T4 | Mandatory co-signer on Irreversibility Gate Record |
| TL | Technical Lead | A | Technical accountability for deployment; executes or supervises execution; verifies on-chain state | Mandatory co-signer on Irreversibility Gate Record |
| vCISO | vCISO | A | Independent verification of all 7 Hard Stops; confirms audit and monitoring status; mandatory co-signer | Mandatory co-signer on Irreversibility Gate Record — gate is invalid without vCISO signature |
| DevOps | DevOps | R | Executes deployment steps per runbook; monitors production from go-live | Deployer role in two-person rule |
| Dev | Developer | R | Supports deployment execution; on-call for 24h post-deployment | N/A |
| DoE | Director of Engineering | C | Required co-approval for T3/T4 engagements; escalation point for any Hard Stop | Must co-sign for T3/T4 deployments |
| AM | Account Manager | I | Informed of go-live; coordinates client communication at go-live (Track B) | N/A |

## 3. Role-Based Checklist

| P9-vCISO-001 Irreversibility Gate: verify all 7 Hard Stop conditions [TRACK A + B] |  |
| --- | --- |
| Step ID | P9-vCISO-001 |
| Phase | Phase 9 — Production Deployment |
| Role | vCISO |
| Control Objective | Verify all 7 Hard Stop conditions are CLEAR before authorizing the irreversible mainnet deployment, preventing deployment of a system with unresolved structural prohibitions. |
| Action | Irreversibility Gate: verify all 7 Hard Stop conditions |
| Detailed Instruction | Complete the Irreversibility Gate Checklist. For each Hard Stop condition, state the verification method and current status (CLEAR / TRIGGERED): HS-01 — OFAC Jurisdiction: Verification: Re-check client entity jurisdiction against OFAC SDN list. Record: List source checked, date, analyst name. Required status: CLEAR. If TRIGGERED: STOP — do not proceed. HS-02 — MSA Signed: Verification: Confirm executed MSA is in legal folder; check signature dates and parties. Required status: CLEAR (MSA signed and in file). If not: STOP — HS-02 breach. HS-03 — TVL/External Audit: Verification: If TVL > $1M or DeFi/Bridge: confirm external audit report is received, all Critical/High findings resolved, and report is signed by audit firm. Required status: CLEAR (audit received and resolved) or N/A (TVL < $1M, not DeFi/Bridge). HS-04 — Concentration: Verification: Check current Node revenue vs. client revenue. If client > 60% of Node revenue: confirm GRC review was completed. Required status: CLEAR or GRC review documented. HS-05 — Payment Arrears: Verification: Confirm with Finance that no invoice is overdue > 60 days. Required status: CLEAR. If TRIGGERED: stop-work per POL-003. HS-06 — Irreversibility Gate Cleared: This condition is cleared by the signing of this Gate Record itself. Verification: Confirm this checklist is complete and all other conditions are CLEAR before Gate Record is signed. HS-07 — Custody Ambiguity: Verification: Confirm admin/control matrix is accurate; key ownership is explicitly assigned; no "TBD" remains for any admin key holder. Required status: CLEAR. If ambiguous: deployment blocked. Document the result for each HS condition. If all are CLEAR: proceed to sign Irreversibility Gate Record. If any TRIGGERED: do not sign — resolve the triggered condition with appropriate authority. |
| Required Input | OFAC SDN list access; executed MSA; external audit report (if applicable); Finance payment status; admin/control matrix (P5-TL-002 current version); PSF current version. |
| Method / Calculation / Assessment | Document verification against each HS condition. Each verification has a named source and date. |
| Expected Output | Irreversibility Gate Checklist (HS-01 through HS-07): all conditions evaluated with CLEAR/TRIGGERED status and verification method documented. |
| Evidence Required | Completed Irreversibility Gate Checklist (vCISO signed, dated, timed). OFAC check source documented. Finance payment confirmation. External audit report reference (if applicable). |
| Approval Required | vCISO completes and signs the checklist. The checklist is a prerequisite for the Irreversibility Gate Record. |
| Acceptance Criteria | All 7 conditions evaluated. All 7 are CLEAR or have documented resolution. No condition is blank. Checklist is signed and timed (timestamp, not just date). |
| Related Risk | HS-01 through HS-07 (all Hard Stops) |
| Related Control | 7-condition Hard Stop verification — mandatory pre-deployment; STD-101 Step 9 |
| Related Policy / Standard Clause | POL-001 §5.3 (Hard Stop conditions); STD-101 Step 9 Gate; POL-009 (exception for any override) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-9-ProductionDeployment/P9-vCISO-001-IrreversibilityGate-Checklist-v1.0-[DATETIME].docx |
| Audit Relevance | This is the most audit-critical single document in the entire lifecycle. External auditors will review every line. Timestamp must precede first mainnet transaction. Any blank or TRIGGERED condition without resolution is a Critical audit finding. |
| Notes / Exceptions | vCISO must complete this checklist independently — do not rely on PM or TL assertions for HS verification. Verify each condition from primary sources. |

| P9-NO-001 Sign Irreversibility Gate Record — authorize production deployment [TRACK A + B] |  |
| --- | --- |
| Step ID | P9-NO-001 |
| Phase | Phase 9 — Production Deployment |
| Role | Node Owner (NO) |
| Control Objective | Provide final business-level accountability sign-off on the production deployment, ensuring the business decision to deploy is made by the correct authority with full awareness of residual risks. |
| Action | Sign Irreversibility Gate Record — authorize production deployment |
| Detailed Instruction | Review the Irreversibility Gate Checklist (P9-vCISO-001). Confirm: 1. All 7 Hard Stop conditions are CLEAR (verified in checklist). 2. External audit report received and all Critical/High resolved (if required). 3. Monitoring is live and validated (P8-DevOps-001). 4. Testnet runbook completed without failures (P8-TL-001). 5. Residual risk summary has been reviewed and accepted. 6. For T3/T4: Director of Engineering has been notified and co-signed. 7. For Track B: client testnet acknowledgement is in project folder. Read the residual risk summary and explicitly acknowledge the following on the gate record: "I [Name], Node Owner, have reviewed the Irreversibility Gate Checklist, confirm all 7 Hard Stop conditions are CLEAR, have read the residual risk summary, and authorize the production deployment of [Protocol Name] for [Client Name] on [Date]." Sign the Irreversibility Gate Record (with TL and vCISO co-signs). The three signatures are mandatory — a partially signed gate record does not authorize deployment. |
| Required Input | Irreversibility Gate Checklist (P9-vCISO-001 complete); residual risk summary; Gate G6 Decision Record. |
| Method / Calculation / Assessment | Review and sign-off. Explicit written acknowledgement statement on gate record. |
| Expected Output | Irreversibility Gate Record signed by: Node Owner + Technical Lead + vCISO (all three). Time-stamped. |
| Evidence Required | Irreversibility Gate Record (three signatures, time-stamped). Physical or digital signatures. PDF copy stored in GW project folder with access restricted to project principals and vCISO. |
| Approval Required | Node Owner + TL + vCISO (all three mandatory). For T3/T4: Director of Engineering co-signs. Without all three signatures: deployment is blocked. |
| Acceptance Criteria | All three signatories have signed. Gate record includes explicit acknowledgement of residual risks and Hard Stop status. Time-stamp precedes first mainnet transaction. |
| Related Risk | HS-06 (gate not cleared before deployment) |
| Related Control | Irreversibility Gate Record — mandatory authorization artifact; STD-101 Step 9 |
| Related Policy / Standard Clause | POL-001 §5.2; STD-101 Step 9 Gate; POL-001 §5.3 (HS-06) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-9-ProductionDeployment/P9-NO-001-IrreversibilityGateRecord-v1.0-[DATETIME].pdf Access: Node Owner, TL, vCISO, DoE (T3/T4), approved auditors only |
| Audit Relevance | Irreversibility Gate Record is the single most important governance document in the lifecycle. Every Big 4 / ISO internal audit will examine this document first. Missing or partial signatures are a Critical finding. |
| Notes / Exceptions | The gate record must be prepared in advance and brought to all three signatories before the deployment window begins. Do not execute deployment steps while waiting for signatures. |

| P9-TL-001 Execute mainnet deployment (two-person rule) and verify on-chain state [TRACK A + B] |  |
| --- | --- |
| Step ID | P9-TL-001 |
| Phase | Phase 9 — Production Deployment |
| Role | Technical Lead (TL) |
| Control Objective | Execute mainnet deployment per the validated testnet runbook with two-person rule, then verify all on-chain state is correct before any public announcement. |
| Action | Execute mainnet deployment (two-person rule) and verify on-chain state |
| Detailed Instruction | Execute using the SAME runbook used at testnet (P8-TL-001), updated with mainnet-specific parameters (RPC endpoint, gas price, deployer address for mainnet). Pre-execution: [ ] Confirm Irreversibility Gate Record is signed by all three signatories (NO + TL + vCISO). [ ] Confirm production monitoring is live (not just configured — verify dashboard is showing live data). [ ] Confirm deployer (DevOps) and approver (TL) are both available and in contact. [ ] Confirm two-person attestation mechanism (call, video call, or co-located). Execution: [ ] Follow runbook step-by-step. No ad-hoc changes — any deviation from runbook requires TL + vCISO authorization before proceeding. [ ] Record each transaction hash and block number in real-time. Post-deployment on-chain verification (mandatory before public announcement): [ ] Call owner() on each deployed contract — verify returns expected multisig address. [ ] Call paused() (or equivalent) — verify protocol is in expected initial state. [ ] Verify multisig is active: attempt a test multisig proposal and confirm it requires N-of-M signatures. [ ] Confirm timelock is active (if applicable): propose a change and verify timelock delay. [ ] Verify monitoring is receiving events from the new mainnet deployment (not testnet). [ ] Record all verified on-chain state: address, function called, expected result, actual result, block number. Public announcement: NO GO-LIVE ANNOUNCEMENT until all on-chain verification steps are complete and signed. |
| Required Input | Signed Irreversibility Gate Record; validated mainnet runbook; mainnet deployer wallet; mainnet RPC access. |
| Method / Calculation / Assessment | Sequential runbook execution. Two-person rule (DevOps deploys, TL approves each critical step). On-chain state verification from a separate RPC node. |
| Expected Output | Completed mainnet deployment runbook (all steps checked, real txhashes). On-chain verification record. |
| Evidence Required | Completed mainnet runbook (DevOps + TL signed, time-stamped). On-chain verification record (TL signed): each function call, result, block number. Mainnet explorer links to each contract. |
| Approval Required | TL (technical approver, two-person rule). DevOps (executor). vCISO receives copy of deployment completion within 1 hour. |
| Acceptance Criteria | All runbook steps completed. All on-chain verification checks pass. Owner() returns multisig address. Monitoring is live on mainnet. No announcement made before on-chain verification complete. |
| Related Risk | DEPLOY-FATAL-01; PAUSE-FATAL-01; HS-07 |
| Related Control | Mainnet deployment with verification — STD-101 Step 9; two-person rule; on-chain state verification |
| Related Policy / Standard Clause | POL-004 §2.5 (two-person rule); STD-101 Step 9 Hard Stop; POL-005 §3.2 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-9-ProductionDeployment/P9-TL-001-MainnetRunbook-Completed-v1.0-[DATETIME].docx P9-TL-001-OnChainVerification-v1.0-[DATETIME].docx |
| Audit Relevance | Mainnet deployment record with real transaction hashes is primary Phase 9 audit evidence. Auditors will verify transaction hashes on-chain. Missing hashes or mismatched addresses are Critical findings. |
| Notes / Exceptions | If any on-chain verification step fails: STOP. Do not announce go-live. Invoke incident response procedure and notify vCISO immediately. |

| P9-AM-001 [TRACK B ONLY] Client go-live consent and announcement coordination [TRACK B] |  |
| --- | --- |
| Step ID | P9-AM-001 |
| Phase | Phase 9 — Production Deployment |
| Role | Account Manager (AM) |
| Control Objective | For Track B: obtain formal client go-live consent and coordinate client-facing public announcement to ensure client ownership of the deployment decision. |
| Action | [TRACK B ONLY] Client go-live consent and announcement coordination |
| Detailed Instruction | For Track B only. Before the mainnet deployment begins: 1. Confirm with client Product Owner that they have reviewed and signed off on the testnet acknowledgement (P8-TL-004). 2. Confirm client is aware of the deployment window date and time. 3. Confirm client has the support contact (vCISO + TL) for the 24 hours post-deployment. 4. Obtain client written consent for go-live: email from client Product Owner confirming they authorize the mainnet deployment. At the time of deployment: 5. Keep client contact informed: notify when deployment starts, when on-chain verification is complete. 6. Coordinate public announcement: if Protofire or client will make a public announcement (blog, Twitter/X, press release), confirm that announcement timing is AFTER on-chain verification is complete and monitoring is confirmed live. 7. Agree with client on who is the primary contact for the first 48 hours post-deployment (TL or DevOps on-call). |
| Required Input | Testnet acknowledgement (P8-TL-004); deployment window schedule; client contact details. |
| Method / Calculation / Assessment | Written client consent email. Announcement coordination plan documented. |
| Expected Output | Client go-live consent email. Announcement coordination record. |
| Evidence Required | Client go-live consent email (PDF export, named client signatory, dated). Announcement coordination plan (if applicable). |
| Approval Required | Node Owner informed. vCISO confirms no security concerns with public announcement timing. |
| Acceptance Criteria | Written client consent from named representative. Announcement (if any) is scheduled after on-chain verification. Client has support contact for 48h post-deployment. |
| Related Risk | REPUT-02 (blame transfer if client claims they were not consulted on go-live) |
| Related Control | Client go-live consent — Track B accountability |
| Related Policy / Standard Clause | POL-001 §5.1 (Track B); POL-008 §2 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-9-ProductionDeployment/P9-AM-001-TrackB-GoLiveConsent-[DATE].pdf |
| Audit Relevance | Track B client go-live consent is evidence that the deployment was client-authorized. In a dispute, this document establishes that the client explicitly requested the mainnet deployment. |
| Notes / Exceptions | TRACK B ONLY. If client fails to provide consent within 24 hours of scheduled deployment window: contact Node Owner. Do not deploy without consent unless Node Owner makes an explicit decision to proceed (which must be documented). |

# Phase 10: Maintenance / Support

| OPERATIONS | Track A + Track B — Track B requires formal client acceptance document and client-signed security posture document acknowledgement |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 10 |
| --- | --- |
| Phase Name | Maintenance / Support |
| Phase Objective | Manage ongoing operations within clearly defined support boundaries. Prevent responsibility creep. Document key ownership transfer. Deliver the Security Posture Document to client. Maintain monitoring continuity until handover is complete. Establish the ongoing KRI monitoring cadence. |
| Entry Criteria | Phase 9 complete — mainnet deployment verified on-chain Irreversibility Gate Record signed Monitoring live on mainnet Support boundaries agreed (or to be formalized in this phase) |
| Exit Criteria | Formal client acceptance signed Support boundaries documented and client-acknowledged Key ownership transferred or explicitly retained with documentation Security Posture Document delivered Monitoring handover confirmed Phase 10 KRI baseline established |
| Key Phase Risks | OPS-01 — Responsibility creep (client assumes unlimited support outside agreed scope) REPUT-02 — Client ignores guidance, incurs loss, attributes blame to Protofire SEC-POST-01 — Critical vulnerability identified post-handover with unclear responsibility MON-01 — Monitoring gap during handover period |
| Key Control Objectives | Support scope documented in writing and client-acknowledged before handover complete Key ownership transfer documented and on-chain verifiable Security Posture Document delivered before closing the delivery engagement Monitoring continuity maintained without interruption through handover |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — Track B requires formal client acceptance document and client-signed security posture document acknowledgement |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-10-Maintenance/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-10/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P10-[ROLE]-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| NO | Node Owner | A | Accountable for clean handover; confirms support boundaries; signs acceptance record | Signs Gate G8-A acceptance record |
| AM | Account Manager | R | Manages client relationship; ensures acceptance is signed; tracks support requests | Co-signs acceptance record |
| TL | Technical Lead | R | Delivers Security Posture Document; confirms key ownership transfer; provides ongoing technical support within scope | Signs Security Posture Document |
| vCISO | vCISO | C | Reviews Security Posture Document; confirms monitoring continuity; activates Phase 10 KRI monitoring | Co-signs Security Posture Document for T3/T4 |
| DevOps | DevOps | C | Confirms monitoring handover; ensures alert recipients are correct for ongoing operations | N/A |
| PM | Project Manager | I | Tracks open items to formal close; confirms delivery phase artifacts are complete | N/A |
| CUST | Customer/Product Owner | I | Track B: signs acceptance document; acknowledges Security Posture Document; defines their ongoing support contact | Track B: signs acceptance document |

## 3. Role-Based Checklist

| P10-NO-001 Document and obtain acknowledgement of support boundaries [TRACK A + B] |  |
| --- | --- |
| Step ID | P10-NO-001 |
| Phase | Phase 10 — Maintenance / Support |
| Role | Node Owner (NO) |
| Control Objective | Ensure support boundaries are formally documented and client-acknowledged, preventing unlimited or undefined support obligations that create liability and resource risk. |
| Action | Document and obtain acknowledgement of support boundaries |
| Detailed Instruction | Prepare the Support Scope Document covering: 1. In-scope support: - Bug fixes for code authored by Protofire (within X months of go-live, or as contractually agreed) - Critical security patch response (24-hour SLA for Critical; 5-day for High) - Monitoring alert triage (first responder within X hours) - Documentation updates - Responding to queries within agreed response time 2. Out-of-scope (must be explicitly listed): - Protocol economic decisions (yield rates, fee changes) — client responsibility - Protocol governance decisions — client/DAO responsibility - Third-party protocol changes (oracle provider changes, bridge upgrades) - New feature development (requires new SOW/MSA) - Infrastructure management if client takes over hosting 3. Key ownership and custody boundaries: - Who holds admin keys post-handover (client / Protofire / shared multisig) - Who holds upgrade keys (if applicable) - If Protofire holds any keys: what is the key rotation policy and when are keys transferred to client? 4. Escalation path for security incidents: - Primary contact: [TL name + contact] - Secondary contact: vCISO [contact] - Protocol for suspected exploit: [steps — who does what in first 30 minutes] 5. Support duration: [X months from go-live date, per MSA] For Track B: obtain written client acknowledgement of this document before the delivery engagement is considered closed. |
| Required Input | MSA (support terms section); PSF; admin/control matrix; key ownership intent from Phase 4–9. |
| Method / Calculation / Assessment | Document preparation and client sign-off process. For Track A: internal sign-off by NO and AM. For Track B: client signature required. |
| Expected Output | Support Scope Document (signed by NO and AM). Track B: client countersigned. |
| Evidence Required | Support Scope Document (signed, versioned). Track B: client countersignature (email or wet/digital signature on document). |
| Approval Required | Node Owner signs. AM signs. Track B: client Product Owner acknowledges. |
| Acceptance Criteria | Document exists with all 5 sections completed. In-scope and out-of-scope are explicitly listed (no vague language). Key ownership is unambiguous. Client acknowledgement received (Track B) or internal sign-off complete (Track A). |
| Related Risk | OPS-01 (responsibility creep); REPUT-02 (blame transfer) |
| Related Control | Support boundary documentation — STD-101 Step 10; POL-008 §2 |
| Related Policy / Standard Clause | STD-101 Step 10 Preventive Controls; POL-001 §5; POL-008 §2 (retention) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-10-Maintenance/P10-NO-001-SupportScope-v1.0-[DATE].docx |
| Audit Relevance | Support scope document is evidence that responsibility boundaries were formally established. In a dispute, this is the primary contractual reference for what Protofire was obligated to do post-delivery. |
| Notes / Exceptions | If the MSA is silent on support duration or scope, negotiate an addendum or supplemental agreement before the delivery team is disbanded. Do not allow informal support to continue without written boundaries. |

| P10-TL-001 Produce and deliver Security Posture Document (SPD) [TRACK A + B] |  |
| --- | --- |
| Step ID | P10-TL-001 |
| Phase | Phase 10 — Maintenance / Support |
| Role | Technical Lead (TL) |
| Control Objective | Deliver a Security Posture Document that enables the client to understand and manage the residual risks of the deployed system independently. |
| Action | Produce and deliver Security Posture Document (SPD) |
| Detailed Instruction | The Security Posture Document is the technical handover document for the security posture of the deployed system. It must be intelligible to a non-technical stakeholder (read by client, by auditors, by incident responders). SPD sections (mandatory): 1. Deployed System Summary: - Contract addresses (mainnet, all chains) - Protocol version deployed - Deployment date and deploying party - Admin/control matrix (link to Phase 5 document; confirm it is current) 2. Residual Risks (plain English): - List every accepted risk from the internal audit, economic simulation, and threat model that was not fully mitigated. - For each: risk description, likelihood, recommended action for client. - Do NOT use jargon — write for a non-technical board member. 3. Known Limitations and Design Tradeoffs: - Any design decision that prioritized performance or cost over maximum security (explain why). - Any feature that was descoped and what the security implication is. 4. Recommended Actions for Client: - "You should monitor X using tool Y." - "You should upgrade library Z when version A is released." - "You should not enable feature B until external audit of that feature is complete." 5. Incident Response Quick Reference: - Suspected exploit: [exact steps — who to call, what to do first] - Pause function: [how to invoke, who has the key] - External communication: [who speaks publicly on behalf of the protocol in an incident] 6. External Audit Status: - Audit firm, scope, date, all findings and resolution status. 7. Contact Directory: - Protofire contacts (TL, vCISO) with communication method and response time SLA. |
| Required Input | All Phase 5–9 evidence: threat model, internal audit report, economic simulation, external audit (if applicable), admin matrix, residual risk summary. |
| Method / Calculation / Assessment | Document preparation. vCISO reviews before delivery to client. |
| Expected Output | Security Posture Document v1.0 (all 7 sections complete, signed by TL, reviewed by vCISO). |
| Evidence Required | Security Posture Document (TL signed, vCISO reviewed). Client delivery confirmation (email with attachment, or client signature on document cover). |
| Approval Required | vCISO reviews and signs for T3/T4. TL signs all tiers. |
| Acceptance Criteria | All 7 sections complete. No jargon in residual risk section. All residual risks from audit acceptance records are included. Contact directory is current. Client delivery is documented. |
| Related Risk | REPUT-02 (blame transfer if risks not communicated); OPS-01; SEC-POST-01 |
| Related Control | Security Posture Document — STD-101 Step 10; POL-008 §2 |
| Related Policy / Standard Clause | STD-101 Step 10; POL-002 §3.6 (ongoing security obligations); POL-008 §2 |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-10-Maintenance/P10-TL-001-SecurityPostureDocument-v1.0-[DATE].docx Client copy: delivered via agreed mechanism; Protofire retains signed copy |
| Audit Relevance | Security Posture Document is evidence that client was informed of residual risks at handover. Absence of this document is a High-severity finding for ISO 27001 Cl.8.29 compliance. |
| Notes / Exceptions | Track B: obtain client signature on the SPD cover page confirming receipt. Track A: internal sign-off by NO and vCISO is sufficient. |

| P10-vCISO-001 Activate Phase 10 KRI monitoring cadence and confirm monitoring handover [TRACK A + B] |  |
| --- | --- |
| Step ID | P10-vCISO-001 |
| Phase | Phase 10 — Maintenance / Support |
| Role | vCISO |
| Control Objective | Activate the KRI monitoring programme for this engagement and establish the monitoring cadence for the operations phase. |
| Action | Activate Phase 10 KRI monitoring cadence and confirm monitoring handover |
| Detailed Instruction | At Phase 10 start, activate the following monitoring activities: 1. On-chain monitoring (continuous): - Confirm monitoring tool is switched to production mainnet addresses (not testnet). - Confirm vCISO is an alert recipient. - If monitoring is being handed to client: document the handover — who receives alerts, escalation path, date of transfer. 2. Monthly KRI review: - Add this engagement to the monthly KRI review schedule. - For Phase 10, track: KRI-01: Unresolved Critical vulns (target: 0) KRI-06: Payment arrears (if ongoing support fee applies) KRI-04: Overdue exceptions (from exception register) KRI-08: Access review overdue 3. Quarterly access review: - Schedule the first quarterly access review for 90 days from go-live. - Review will cover: who has access to protocol admin keys (per admin matrix); who has access to GW project folder; any access granted during delivery that should be revoked. 4. Security awareness follow-up: - Confirm all delivery team members have completed security awareness training (or record if completed during delivery). 5. Anomaly detection: - If a monitoring alert fires in the first 30 days: treat as potential serious incident until confirmed otherwise. Escalation: vCISO → TL → NO within 30 minutes of alert receipt. |
| Required Input | Monitoring configuration (P8-DevOps-001); admin/control matrix; GW project folder access list. |
| Method / Calculation / Assessment | Monitoring tool configuration update (mainnet addresses). KRI schedule update. Calendar entries for quarterly access review. |
| Expected Output | Monitoring Handover Record (if client takes over monitoring). KRI baseline record for this engagement. Quarterly access review scheduled. |
| Evidence Required | Monitoring dashboard screenshot (production addresses, live). KRI baseline record. Quarterly access review calendar confirmation. |
| Approval Required | vCISO owns this step. Node Owner is informed. |
| Acceptance Criteria | Monitoring is confirmed live on mainnet addresses. vCISO is a current alert recipient. KRI review scheduled. Quarterly access review scheduled within 90 days. |
| Related Risk | MON-01 (monitoring gap); SEC-POST-01 (post-handover vulnerability) |
| Related Control | KRI monitoring activation; access review scheduling — POL-010 |
| Related Policy / Standard Clause | POL-010 §2 (monitoring schedule); POL-010 §3 (KRI dashboard); POL-004 §2.6 (quarterly access review) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-10-Maintenance/P10-vCISO-001-MonitoringActivation-v1.0-[DATE].docx |
| Audit Relevance | Monitoring activation record confirms that POL-010 continuous monitoring requirement was implemented at go-live, not retrospectively. |
| Notes / Exceptions | If monitoring responsibility is fully transferred to client: obtain written client confirmation that they accept monitoring responsibility, name the client monitoring contact, and document the alert escalation path to Protofire for any critical event (even post-handover). |

# Phase 11: Upgrade

| OPERATIONS | Track A + Track B — Track B requires client authorization for any on-chain upgrade (C5 change); both tracks follow POL-005 change classification |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 11 |
| --- | --- |
| Phase Name | Upgrade |
| Phase Objective | Manage post-deployment upgrades safely. Any on-chain upgrade re-triggers a mini-cycle through the relevant delivery gates per POL-005. The classification of the change (C1–C5) determines the approval chain and gate requirements. For on-chain upgrades with TVL > $1M: the full Steps 5→8→9 mini-cycle applies. |
| Entry Criteria | Phase 10 active (protocol in production) Change request documented and classified per POL-005 Approval chain determined per change class |
| Exit Criteria | Change classification documented Appropriate approval chain completed Regression testing passed Two-person attestation for on-chain changes Post-upgrade monitoring confirmed active Change record closed in REG-509 |
| Key Phase Risks | SEC-POST-01 — New vulnerability introduced by upgrade DEPLOY-FATAL-01 — Upgrade deploys to wrong address or wrong ownership All Phase 6 and Phase 9 risks re-apply for C5 on-chain upgrades above threshold |
| Key Control Objectives | Change classification mandatory before any upgrade activity On-chain upgrades with TVL > $1M: full mini-cycle required (POL-005 §3.2) Regression testing required before any upgrade Two-person rule applies to all on-chain upgrade execution Post-upgrade monitoring verification required |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — Track B requires client authorization for any on-chain upgrade (C5 change); both tracks follow POL-005 change classification |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-11-Upgrade/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-11/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P11-[ROLE]-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| TL | Technical Lead | A | Leads technical change assessment; determines mini-cycle requirements; signs upgrade runbook | Approves all C2–C5 changes |
| NO | Node Owner | A | Approves C3–C5 changes; authorizes on-chain upgrade with TVL > $1M mini-cycle | Signs C3/C4/C5 change approval |
| Dev | Developer | R | Implements the upgrade; executes regression testing | N/A |
| QA | QA Engineer | R | Executes regression test plan; confirms all affected functions pass | Signs regression test report |
| DevOps | DevOps | R | Executes deployment (two-person rule — Deployer role); verifies post-upgrade monitoring | Deployer in two-person rule |
| vCISO | vCISO | C | Reviews C4/C5 changes; confirms whether mini-cycle is required; confirms post-upgrade monitoring | Co-approves C4/C5 changes |
| PM | Project Manager | I | Tracks change in REG-509; coordinates regression test schedule | N/A |

## 3. Role-Based Checklist

| P11-TL-001 Classify the change and determine mini-cycle requirements [TRACK A + B] |  |
| --- | --- |
| Step ID | P11-TL-001 |
| Phase | Phase 11 — Upgrade |
| Role | Technical Lead (TL) |
| Control Objective | Ensure every upgrade is formally classified before any work begins, determining the correct approval chain and gate requirements. |
| Action | Classify the change and determine mini-cycle requirements |
| Detailed Instruction | Using the change classification model from POL-005 §2: C1 — Standard Change: Criteria: Routine config updates, minor UI fixes, dependency patch (no smart contract changes). Approval: TL review + Developer. Gate: None. Change record in REG-509. C2 — Significant Change: Criteria: Feature additions, non-security-critical contract changes, API changes, testnet update. Approval: TL + QA review + PM sign-off. Gate: Regression test report required. C3 — Major Change: Criteria: Architecture changes, new integrations, scope expansion, any smart contract change that modifies core logic. Approval: NO + TL + vCISO advisory. Gate: Restart Phase 5 (threat model update) and Phase 6 gates for affected scope. C4 — Emergency Change: Criteria: Critical security patch, incident response fix. Approval: vCISO authorizes; NO notified; retrospective documentation within 24h. Gate: Post-implementation review within 24h. C5 — On-Chain Change: Criteria: Smart contract upgrade, ownership transfer, parameter change that modifies on-chain state permanently. Approval: TL + NO + vCISO + two-person rule. Gate: If TVL > $1M: full mini-cycle (Phases 5→8→9). If TVL ≤ $1M: regression test + testnet deployment + two-person production execution. Document the classification with rationale. If there is disagreement on classification: escalate to vCISO for determination. |
| Required Input | Change request description from PM/Dev. Current admin/control matrix. TVL current value. |
| Method / Calculation / Assessment | Classification matrix from POL-005 applied to change description. Written classification record with rationale. |
| Expected Output | Change Classification Record: classification (C1–C5), rationale, approval chain, gate requirements, mini-cycle trigger (Y/N). |
| Evidence Required | Change Classification Record (TL signed, dated). Ticket/issue in project management system cross-referenced. REG-509 entry created. |
| Approval Required | TL signs classification. For C5 mini-cycle trigger: vCISO must confirm classification is correct. |
| Acceptance Criteria | Classification is one of C1–C5. Rationale is specific (not generic). Mini-cycle requirement is explicit for C5. REG-509 entry is created. |
| Related Risk | SEC-POST-01; DEPLOY-FATAL-01 |
| Related Control | Change classification — POL-005 §2; STD-101 Step 11 |
| Related Policy / Standard Clause | POL-005 §2 (change classification); STD-101 Step 11; RACI-001 §7 (upgrade section) |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-11-Upgrade/P11-TL-001-ChangeClassification-v[N]-[DATE].docx REG-509 entry: in the change management log |
| Audit Relevance | Change classification is the audit entry point for all upgrade activity. Auditors will verify classification before reviewing execution evidence. |
| Notes / Exceptions | If the same change could be classified as C4 (emergency) to avoid the C5 mini-cycle, this is a control bypass — do not do it. Contact vCISO if there is genuine urgency for a C5 change. |

| P11-QA-001 Execute regression test plan for the upgrade scope [TRACK A + B] |  |
| --- | --- |
| Step ID | P11-QA-001 |
| Phase | Phase 11 — Upgrade |
| Role | QA Engineer (QA) |
| Control Objective | Verify that no regression was introduced by the upgrade and that all functions affected by the change pass testing before production upgrade is executed. |
| Action | Execute regression test plan for the upgrade scope |
| Detailed Instruction | Before production upgrade execution (for C2 and above): 1. Define regression test scope: - All functions directly modified by the change. - All functions that call or are called by the modified functions (integration scope). - All functions listed in the admin/control matrix (always in scope for any C5 change). 2. Regression test plan (for C2+): - List each test case: function tested, input, expected output, actual output, pass/fail. - Include gas consumption tests for any function that was modified. - For C5: add testnet deployment of the upgrade and run regression tests on testnet before production. 3. Execute regression tests: - Run on testnet for C3/C5. - Run on a forked mainnet (Hardhat fork or Foundry fork) for C2. - Document test run: date, environment, commit hash, tool version. 4. If any regression test fails: - Severity classify the failure. - If Critical/High: block upgrade. Notify TL. Fix and re-run. - If Medium/Low: document in regression report with remediation plan. 5. Sign regression test report. |
| Required Input | Change description; original test suite; modified code (pre-production). |
| Method / Calculation / Assessment | Test execution on appropriate environment. Results documented per test case. |
| Expected Output | Regression Test Report: all test cases documented, all pass/fail results recorded, signed by QA. |
| Evidence Required | Regression Test Report (QA signed). Test output logs (automated where possible). Testnet deployment transaction hashes for C5 regression tests. |
| Approval Required | TL reviews regression report before production upgrade. For any Critical/High failure: TL must authorize a hold. |
| Acceptance Criteria | All test cases in scope executed. All Critical/High regressions resolved before production upgrade. Test report signed by QA. For C5: testnet deployment transaction hashes present. |
| Related Risk | SEC-POST-01 (regression introducing vulnerability) |
| Related Control | Regression testing — POL-006 §2 (Phase 10/11 row); STD-101 Step 11 |
| Related Policy / Standard Clause | POL-006 §2 (regression testing requirement); STD-101 Step 11 Gate criteria |
| Storage Location | Google Workspace: /[Client]/[Project]/GRC/Phase-11-Upgrade/P11-QA-001-RegressionTest-v[N]-[DATE].docx |
| Audit Relevance | Regression test report is evidence that testing occurred before upgrade. Auditors will check that the test commit hash matches the production upgrade commit. |
| Notes / Exceptions | Track B: if client is a co-developer and contributed code to the upgrade, the regression test scope must include their code. Track B client code is subject to the same review standards as Protofire code. |

# Phase 12: New Deployments

| RESTART | Track A + Track B — all 12 lifecycle steps restart for the new engagement; prior history informs but does not bypass new scoring and gates |
| --- | --- |

## 1. Phase Overview

| Phase Number | Phase 12 |
| --- | --- |
| Phase Name | New Deployments |
| Phase Objective | Formally initiate a new project engagement with a full lifecycle restart. Prior engagement history informs but does not substitute for the new engagement risk scoring and gate process. All prior HS conditions must be resolved before the new Phase 3 (MSA) gate. The new engagement must have its own RACI, PSF, and gate records. |
| Entry Criteria | Prior engagement formally closed (or explicitly defined boundary between prior and new) New project opportunity identified No open HS conditions from prior engagement (or conditions documented with resolution) |
| Exit Criteria | New engagement formally opened in project management system Prior engagement close-out record complete New C/B/P score documented New Gate G1-A signed for the new engagement All Phase 1 steps completed for the new engagement |
| Key Phase Risks | REPUT-01 — Reputational risk from prior engagement carried into new engagement without disclosure OPS-01 — Scope of new engagement conflated with ongoing support from prior engagement Prior HS condition from existing engagement not resolved before new engagement begins |
| Key Control Objectives | New C/B/P score is required for every new engagement — prior score cannot be reused Prior engagement formally closed with close-out record before new engagement begins Any unresolved HS condition from prior engagement blocks new Phase 3 gate |
| Track A Description | Protofire retains full delivery ownership. Client has limited visibility. Internal governance standards apply. |
| Track B Description | Client is actively involved as co-delivery partner. Client approval required at key gates. Customer signs specific evidence artifacts. |
| Track Separation Note | Track A + Track B — all 12 lifecycle steps restart for the new engagement; prior history informs but does not bypass new scoring and gates |
| Evidence Storage — Google Workspace | Google Workspace: /[Client]/[Project]/GRC/Phase-12-NewDeployments/ |
| Evidence Storage — Repository | Repository: /docs/governance/phase-12/ |
| Document Naming Convention | [CLIENT]-[PROJECT]-P12-[ROLE]-[STEP_ID]-v[VERSION]-[YYYYMMDD]-[STATUS].docx |
| Access Control | Project folder read access: Node Owner, PM, TL, vCISO. Write access: role specified per step. Audit access: vCISO + approved auditors only. |
| Retention Period | Per POL-008: gate records 5 years; legal docs 7 years; access records 3 years |

## 2. Roles in Scope

| Code | Role Name | RACI | Responsibility in This Phase | Approval Authority |
| --- | --- | --- | --- | --- |
| NO | Node Owner | A | Confirms prior engagement closure; authorizes new engagement initiation; reviews new C/B/P score | Signs new Gate G1-A for new engagement |
| AM | Account Manager | R | Opens new engagement in project system; completes new C/B/P score; closes prior engagement record | Confirms new engagement is distinct from prior |
| PM | Project Manager | R | Sets up new project folder; ensures new evidence structure is created for new engagement | N/A |
| vCISO | vCISO | C | Confirms no open HS conditions from prior engagement; reviews new engagement if T3/T4 | Co-signs new Gate G1-A for new T3/T4 engagement |
| TL | Technical Lead | I | Confirms technical scope of new engagement is documented as distinct from prior | N/A |

## 3. Role-Based Checklist

| P12-AM-001 Close prior engagement and open new engagement in project system [TRACK A + B] |  |
| --- | --- |
| Step ID | P12-AM-001 |
| Phase | Phase 12 — New Deployments |
| Role | Account Manager (AM) |
| Control Objective | Ensure the prior engagement is formally closed before the new engagement begins, preventing scope confusion and evidence commingling. |
| Action | Close prior engagement and open new engagement in project system |
| Detailed Instruction | Before initiating the new engagement: 1. Prior engagement close-out: - Confirm all Phase 10 deliverables are complete (Support Scope Document, Security Posture Document, client acceptance). - Confirm the delivery team has been removed from any access that is no longer required (access review per POL-004 §2.2 — deprovisioning within 1 business day). - Close the project in the project management system with status "COMPLETE" and date. - Record the close-out in the GW project folder: prior engagement close-out record. 2. New engagement initiation: - Create a new project in the project management system with a new project code. - Create a new GW project folder structure: /[Client]/[NewProject]/GRC/Phase-1-Assessment/ etc. - Confirm the new engagement has a distinct scope that is not an extension of prior support (if it IS an extension, it should be handled as a Phase 11 upgrade, not a new Phase 1). 3. Scope boundary documentation: - Document what ends (prior engagement) vs. what begins (new engagement). - Confirm client billing is reset (new invoicing, new payment monitoring in Finance). 4. Verify no open HS conditions from prior engagement remain: - Check prior engagement exception register (REG-506) for any open exceptions. - Check prior engagement Hard Stop records for any unresolved conditions. - If any open HS condition from prior engagement relates to the client entity: new Phase 3 gate is blocked until resolved. |
| Required Input | Prior engagement project folder; Phase 10 close-out confirmation; project management system. |
| Method / Calculation / Assessment | System update (prior project closed; new project created). Document verification. |
| Expected Output | Prior engagement close-out record. New project system entry. New GW folder structure. |
| Evidence Required | Prior engagement close-out record (AM signed, NO notified). New project system record (project code, start date). New GW folder structure (can be screenshot). |
| Approval Required | Node Owner confirms prior engagement is closed. AM opens new engagement. |
| Acceptance Criteria | Prior project marked COMPLETE in system. New project created with distinct code. New GW folder structure exists. Scope boundary documented. No open HS conditions from prior engagement (or documented resolution). |
| Related Risk | OPS-01; REPUT-01 |
| Related Control | Engagement boundary management — STD-101 Step 12; POL-001 §5.1 |
| Related Policy / Standard Clause | STD-101 Step 12; POL-008 §2 (retention of prior engagement records); POL-004 §2.2 (access deprovisioning) |
| Storage Location | Prior engagement: /[Client]/[Project]/GRC/Phase-12-NewDeployments/P12-AM-001-EngagementCloseOut-[DATE].docx New engagement: /[Client]/[NewProject]/GRC/ (new folder) |
| Audit Relevance | Auditors require a clear boundary between engagements. Without a formal close-out record, it is unclear which gate records and evidence belong to which engagement. |
| Notes / Exceptions | If the "new deployment" is a second deployment of the same protocol on a different chain: this is a C5 change (Phase 11), NOT a new engagement requiring Phase 1 restart — unless the contract code is substantively different. Consult vCISO on classification. |

| P12-NO-001 Authorize new engagement — complete new C/B/P score and Gate G1-A for new project [TRACK A + B] |  |
| --- | --- |
| Step ID | P12-NO-001 |
| Phase | Phase 12 — New Deployments |
| Role | Node Owner (NO) |
| Control Objective | Ensure the new engagement undergoes a full risk re-assessment, not a waived or inherited assessment from the prior engagement. |
| Action | Authorize new engagement — complete new C/B/P score and Gate G1-A for new project |
| Detailed Instruction | For the new engagement, all Phase 1 steps must be completed fresh: 1. New C/B/P scoring: - Prior engagement composite score cannot be reused. - Prior history informs B2 (payment history) and B4 (revenue diversification) sub-scores. - Protocol class and TVL for the new project must be re-assessed independently. - If the client or protocol has changed materially since the prior assessment: all sub-factors must be re-scored from scratch. 2. Hard Stop re-verification: - All 7 HS conditions must be re-checked for the new engagement. - Any HS condition that was TRIGGERED in the prior engagement must be confirmed RESOLVED before new Phase 3 gate. 3. Gate G1-A for new engagement: - New Gate G1-A Decision Record must be created, with reference to the NEW engagement scoring worksheet. - Must not reference the prior engagement gate records as substitute. 4. Node Owner acknowledgement: - If the Node Owner acting for the new engagement is a different person than for the prior engagement: the new Node Owner must review all prior engagement history for any unresolved issues. |
| Required Input | Prior engagement records (for B2 history); new project Assessment Brief; new C/B/P worksheet. |
| Method / Calculation / Assessment | Full Phase 1 process repeated per data1.js steps P1-AM-001 through P1-NO-001. |
| Expected Output | New engagement C/B/P scoring worksheet. New Hard Stop Verification Checklist. New Gate G1-A Decision Record. |
| Evidence Required | New C/B/P worksheet (AM + NO signed). New Hard Stop checklist. New Gate G1-A record. These must reference the new project code, not the prior project code. |
| Approval Required | Node Owner (T1/T2). Node Owner + vCISO (T3/T4). Same approval authority as Phase 1. |
| Acceptance Criteria | New C/B/P score is computed independently. New Gate G1-A references the new project. Prior engagement close-out record (P12-AM-001) is in place. No prior HS condition is unresolved. |
| Related Risk | Inherited risk from prior engagement; undetected HS condition in new engagement |
| Related Control | Full lifecycle restart — prevents prior engagement governance from being inherited without fresh assessment |
| Related Policy / Standard Clause | STD-101 Step 12; POL-001 §5.1; POL-003 §2 (fresh scoring required) |
| Storage Location | New engagement: /[Client]/[NewProject]/GRC/Phase-1-Assessment/P12-NO-001-NewEngagement-Gate-G1A-[DATE].docx |
| Audit Relevance | Auditors verify that new engagements have independent gate records. A Gate G1-A that references a prior project's scoring worksheet is an audit finding — it indicates the engagement did not receive a fresh risk assessment. |
| Notes / Exceptions | Track B: if the same client contact is continuing from the prior engagement, the Track B client acknowledgement steps still apply fresh for the new engagement. Do not assume prior acknowledgements carry over. |