# L2-DEL-101 8-Stage Delivery Governance Procedure (Track A/B)

Document ID: L2-DEL-101
Version: 1.0

Status: Approved

Effective: [YYYY-MM-DD]
Owner: Head of Delivery / PMO

Approved By: Node Owners Council
Review: Quarterly

## 1. Purpose

Define the operational delivery workflow and gates that implement L1 standards across Nodes, using an 8-stage lifecycle and two delivery tracks.

## 2. Lifecycle Stages (Canonical)

- Intake & Rating

- Commercial Structuring

- Scope Definition (Discovery or Waiver) + Kickoff

- Discovery & Architecture Sign-off

- Build & Internal QA

- Security Verification & Testnet + Assurance Decision

- Mainnet/Production Release

- Operate / Support / Upgrade / Closeout

## 3. Track A vs Track B

- Track A: internal incubation; organisation owns product risk.

- Track B: customer owns product risk; customer signatures required for waivers and risk acceptances.

## 4. Gate Rules (Applies to All Nodes)

- Each stage has a required gate task and evidence package.

- No stage advances without gate approval.

- Gate evidence must be linked in ClickUp and stored in the evidence vault.

## 5. Stage-by-Stage Requirements (Minimum)

### Stage 1 — Intake & Rating

Accountable: Node Owner
 Required:

- Project metadata, protocol class, custody indicator, rough TVL/exposure estimate

- Green/Amber/Red rating with rationale

- Note: Red is “default No-Go” unless overridden

### Stage 2 — Commercial Structuring

Accountable: Node Owner + CFO
 Required:

- Deposit/retainer (2–3 weeks cost) plan and evidence received before build start

- Stop rule selection (Green/Amber/Red)

- Acceptance window set to 5 business days

- Exceptions: require Node Owner + CFO written approval

### Stage 3 — Scope Definition (Discovery or Waiver) + Kickoff

Accountable:

- Track B: Customer + Account Manager

- Track A: Node Owner + CFO
 Required:

- Discovery pack OR signed Discovery Waiver

- Kickoff roles, comms channels, evidence folder created

### Stage 4 — Discovery & Architecture Sign-off

Accountable: Tech Lead + Node Owner (risk)
 Required:

- Threat Model (4-domain)

- Admin & Control Matrix

- Multisig+timelock plan

- Customer sign-off evidence (document or archived approval screenshot)

### Stage 5 — Build & Internal QA

Accountable: Tech Lead
 Required:

- Test Evidence Report (coverage targets + privileged function tests)

- Internal audit: 2 independent smart contract reviewers sign-off

- Residual risks recorded in plain English

### Stage 6 — Security Verification & Testnet + Assurance Decision

Accountable: AM (assurance) + Security Lead (readiness)
 Required:

- Testnet runbook execution evidence

- Deployment verification proof (link audited commit to deploy)

- External assurance decision record

- Trigger external audit when custody=yes or TVL>X (per L2-ASSURE-103)

### Stage 7 — Mainnet/Production Release (Irreversibility Gate)

Accountable: Node Owner
 Required:

- Irreversibility Gate checklist completed

- Signing ceremony executed by Node Owner

- Ownership verified on-chain

- Monitoring/on-call readiness evidence

### Stage 8 — Operate/Support/Upgrade/Closeout

Accountable: AM (commercial) + Node Owner (risk)
 Required:

- SLA addendum (Track A business hours; Track B default 24/7 unless contract states otherwise)

- Support boundaries and change/upgrade workflow

- Closeout acceptance record, key/admin ownership clarified

## 6. RACI Summary (Gate Accountability)

- CEO/Board: escalation authority (enterprise-critical)

- Node Owner: gate authority for Node and release decisions

- CFO: financial control approvals and exceptions

- AM: customer-facing risk owner and assurance decision owner

- Tech Lead: design/build quality authority

- Security Lead: security readiness authority